## Slide 1
Project
Reporting
Oversight and
Monitoring
Solution
Working better together
Workarounds for 2024 Agreements
March 2024

## Slide 2
Why Workarounds?

## Slide 3
PROMS digitalizes partnership management process where possible.
PROMS provides a platform to store documents to reduce the need for duplication of documents in an additional archiving system. In addition, it improves collaboration with our partners.
The objective is to onboard as many partners as possible to PROMS and the workarounds is a ‘last resort’ in cases where we cannot onboard a partner to PROMS.
There are inevitably some partners who will never use PROMS – e.g., partners who operate in embargoed countries i.e., Yemen, government entities, and non-funded partners.
Why do we need workarounds?

## Slide 4
Step-by-step guides to outline how to undertake key partnership management processes where the partner does not have any access to Aconex.
All communications with the partner will be facilitated through Outlook email.
These workarounds are applicable for partnership agreements in 2024 and beyond.
What is a Workaround?

## Slide 5
PROJECT FINANCIAL REPORT (PFR)

## Slide 6
Please note that this workflow process is not just about the submission of the PFR (despite the template name). The workflow feeds into the process of documenting the partner’s reporting and UNHCR’s verification process, taking into consideration:
Reported progress against results,
Expenditure to date,
Action taken to follow-up on implementation monitoring recommendations,
Progress against a partner’s PSEA CSIP,
Feedback from people with and for whom the partner/UNHCR works,
Progress against risk treatment plans and ICA/Q recommendations.
This workflow therefore encompasses partner reporting and UNHCR's verification processes, consolidating documentation of UNHCR's implementation monitoring, and hence it is initiated by Programme with Project Control in copy from the start.
Project Financial Report (PFR)

## Slide 7
Project Financial Report (PFR) | (1/3)
PFR is generated in Aconex
UNHCR User (Programme)
Partner User
UNHCR User (Programme)
The PFR template is generated in Aconex via integration and is based on the contents of the final approved financial plan of the project workplan contract (for the first PFR) or it is based on the previous approved PFR (if not the first PFR).
Workflow Steps:
Selects the PFR Excel template from the Aconex Document Register and transmits it on a workflow by selecting the “Project Financial Report Submission” workflow template.
In the “View and Edit Workflow Settings” of the Workflow Wizard, Programme inserts their name for the “participants” in the “Partner PFR Input” step and adds Project Control to be in copy for this first step. Programme also aligns the step deadlines with the PFR deadline requirements listed in the project workplan contract terms (as feasible and applicable).
Programme downloads the PFR once received through the “partner PFR input” step in the workflow, and emails the PFR excel template to the partner via Outlook email.
Opens the PFR excel email attachment, enters expenditures as ‘actuals’, proposed budget variations (and/or reflects new account code expenditure) as ‘reallocations’ (if applicable) and the requested value for the next prepayment amount (if applicable).
NOTE: This may involve meetings / consultations with Project Control and Programme to ensure the partner has filled out their sections of the PFR template correctly.
Creates a PDF version of the excel and adds their signature.
Sends the partner-completed PFR excel and signed PDF back to UNHCR via Outlook email, along with any supporting documents as required (e.g. general ledgers and a payroll report).
Replaces PFR Excel template in the “Partner PFR Input” step with the partner-completed PFR Excel and uploads the signed PDF as a supplementary file.
Uploads any supporting documents sent via Outlook from the partner (e.g. general ledgers and a personnel list) as other supplementary files (if applicable).
Completes the “Partner PFR Input” step of the workflow as “Approved”.
Moves the PFR workflow to “1st Stage Approval” step.

## Slide 8
Project Financial Report (PFR) | (2/3)
UNHCR User (Project Control)
UNHCR User (Programme)
UNHCR User (Programme)
UNHCR User (Project Control)
Downloads the partner-completed PFR Excel from the workflow transmittal via email and commences the financial verification.
Completes the Project Performance Verification, consolidating all monitoring evidence as a desk review and fills out the PMC02 form online via Field Inspections, adding their signature and downloading the closed PMC02 form as a PDF.
Obtains the partner’s acceptance status and their signature on the PMC02 PDF via Outlook email (see separate PMC02 process steps).
Workflow Steps:
Uploads the signed PMC02 PDF into the “1st Stage Approval” step as a supplementary file.
NOTE: Under exceptional circumstances, if there is no need for UNHCR Programme to complete the PMC02 form, they can complete the workflow step by selecting the review outcome of “review not required”.
15. Completes the workflow step as “Approved”.
NOTE: Please do not select the review outcome of “Cancelled” because this will trigger an amendment of the project workplan.
16. Moves the PFR workflow to “2nd Stage Approval” step.
Completes the Project Financial Verification and fills out the PMC03 form online via Field Inspections, adding their signature and obtaining the UNHCR approval signature (from the most senior UNHCR project control focal point).
Downloads the closed PMC03 form as a PDF and sends it to the partner via Outlook email to obtain the partner’s acceptance status and signature on the PDF (see separate PMC03 process steps).

## Slide 9
Project Financial Report (PFR) | (3/3)
UNHCR User (Project Control)
UNHCR User (Project Control)
UNHCR User (Project Control)
UNHCR User (Representative)
Workflow steps:
Uploads the signed PMC03 PDF into the “2nd Stage Approval” step as a supplementary file. NOTE: Under exceptional circumstances, if there is no need for UNHCR Project Control to complete and upload the PMC03 form, they would not add any supplementary files to the workflow step.
Opens the partner-completed PFR from the workflow step and the supplementary files (as applicable).
Workflow steps (cont.):
Enters the verified expenditures as ‘actuals’, agreed budget variations as ‘reallocations’ (if applicable) and the approved next prepayment value (if applicable) into the partner- completed PFR to become the UNHCR-completed PFR.
NOTE: If Project Control does not agree with the partner’s proposed values, they can consult with the partner via email / phone calls / meetings until agreement is met and both the partner and UNHCR values are identical in the Excel (automatically populating the “Agreed” columns).
Workflow steps (cont.):
Uploads the final UNHCR-completed PFR in the workflow step (replacing the partner- completed PFR).
Completes the workflow step as “Approved”.
NOTE: Please do not select the review outcome of “Cancelled” because this will trigger an amendment of the project workplan.
24. Moves the PFR workflow to “3rd Stage Approval” step.
Representative may delegate authority for 3rd stage approval
In “3rd Stage Approval” step, the delegated authority reviews the UNHCR-completed PFR. If there are any concerns, starts a “Representative Sub Workflow” (see step 15 of “Negotiation of Financial Plan”, however Project Control would take the actions in the sub workflow instead of Programme) that has an overall deadline that fits within the deadline of the parent “3rd Stage Approval” step.
If in agreement, completes the workflow step as “Approved”. NOTE: Please do not select the review outcome of “Cancelled” because this will trigger an amendment of the project workplan.
Note: After completion of step 26, the workflow is completed and the PFR submission is approved. The PFR will now have a document status of “approved”, the next PFR template will come through to PROMS via integration and the next prepayment invoice will be automatically generated in Cloud ERP (if applicable).

## Slide 10
PROJECT PERFORMANCE VERIFICATION (PMC02)

## Slide 11
PROJECT PERFORMANCE VERIFICATION (PMC02)
UNHCR User (Programme)
Partner user
UNHCR User (Programme)
Partner User
Completes the Project Performance Verification as a desk review.
Creates a new Field “Inspection” in Aconex using the PMC02 form.
Answers the questions in the PMC02 form in Aconex (can be filled out both offline on a smartphone and online).
Requests for clarifications / additional documents from the partner via Outlook email. If no additional clarifications / additional documents are required, proceeds to Step 7.
Reviews the request for clarifications / additional documents and responds to UNHCR via Outlook email. Process continues until UNHCR’s clarifications have been resolved and/or all necessary additional documents have been received by UNHCR.
Updates the PMC02 form in the Field module, uploading additional documents received from the partner to relevant questions (if applicable).
Signs the PMC02 form in the Field module.
Downloads the PMC02 form as a PDF from Aconex and sends it to the partner via Outlook email.
Opens the PMC02 PDF email attachment and reviews the content.
If the partner does not agree to some of the content, sends an Outlook email response to UNHCR outlining their feedback/concerns (return to step 6).
If the partner agrees to the content, inserts their acceptance status and signs the PDF, then returning it to UNHCR via Outlook email (proceed to step 12).
UNHCR User (Programme)
Opens the completed PMC02 PDF email attachment and saves the file temporarily on the operation’s SharePoint.
Re-enters the PMC02 form in the Field module and completes the partner’s section, uploading the partner-signed PMC02 as an attachment. The PMC02 is closed with all mandatory fields completed.
*NOTE: The fully completed closed PMC02 is PDF-ed and uploaded to the applicable PFR workflow. If the PMC02 is completed outside the need for a PFR submission, the closed PMC02 is PDF-ed and uploaded to the Document Register in PROMS as the document type “inspection” and then “PMC02” as the “inspection type”.

## Slide 12
PROJECT FINANCIAL VERIFICATION (PMC03)

## Slide 13
PROJECT FINANCIAL VERIFICATION (PMC03) | (1/2)
UNHCR User (Project Control)
Partner User
UNHCR User (Project Control)
UNHCR User (Approver)
Completes the Project Financial Verification.
Creates a new Field “Inspection” in Aconex using the PMC03 form (either short or long form).
Answers the questions in the PMC03 in Acone, uploading supporting documentation as required.
Requests for clarifications / additional documents from the partner via Outlook email. If no additional clarifications / additional documents are required, proceeds to Step 6.
Reviews the request for clarifications / additional documents and responds to UNHCR via Outlook email. Process continues until UNHCR’s clarifications have been resolved and/or all necessary additional documents have been received by UNHCR.
Updates the PMC03 form in the Field module, uploading additional documents received from the partner to relevant questions (if applicable).
Signs the PMC03 form in the Field module and assigns it to the UNHCR approver.
Approves the PMC03, as the most senior UNHCR project control focal point, by adding the approval signature.

## Slide 14
PROJECT FINANCIAL VERIFICATION (PMC03) | (2/2)
UNHCR User (Project Control)
Partner User
UNHCR User (Project Control)
Downloads the PMC03 form as a PDF from Aconex and sends it to the partner via Outlook email.
Opens the PMC03 PDF email attachment and reviews the content.
If the partner does not agree to some of the content, sends an Outlook email response to UNHCR outlining their feedback/concerns (return to step 6).
If the partner agrees to the content, inserts their acceptance status and signs the PDF, returning it to UNHCR via Outlook email (proceed to step 13).
Opens the PMC03 PDF email attachment and saves the file temporarily on the operation’s SharePoint.
Re-enters the PMC03 form in the Field module and completes the partner’s section, uploading the partner-signed PMC03 as an attachment. The PMC03 is closed with all mandatory fields completed.
NOTE: The fully completed closed PMC03 is PDF-ed and uploaded to the applicable PFR workflow.
* NOTE: If the PMC03 is completed outside the need for a PFR submission, the closed PMC02 is PDF-ed and uploaded to the Document Register in PROMS as the document type “inspection” and then “PMC02” as the “inspection type”.