## Slide 1
Project
Reporting
Oversight and
Monitoring
Solution
Working better together
Train-of-Trainer Workshop – Process Overview
September 2023

## Slide 2
CLOUD ERP LINKAGE WITH PROMS

## Slide 3
BIG PICTURE – PROMS FUNCTIONALITY
PROMS IN PRACTICE
PROMS
Other Systems
Audits and Closure
Commence project audit
8
Receive Response to Enquiry for Information
Submit Enquiry for Information via Mail module
Submit Request for Payment for unspent balances / audit recoveries
Receive Response
Verify Payment has been made in Cloud ERP
10
Submit Partner Agreement Closure Request via Mail module
Approval of Request
Update Status of Contract
Update Status of Partnership Agreement
11
Auditor uploads draft audit report
UNHCR uploads audit recommendations
Auditor transmits audit report to partner via a workflow
UNHCR transmits audit recommendations to partner via a workflow
9
Partner created as a “Supplier” in Cloud ERP and available in COMPASS
Partner registers in Aconex
Partner registration in UNPP
1
2
ICA in UNPP / PROMS
3
Create Purchase Order (PO)
Register digital PDF Copy of PO
Release Initial Instalment & Create, Validate & Release Prepayment Invoice
Register Digital PDF Copy of Certificate of Instalment
4
Complete final workflow step for Financial Plan and Results Plan respectively
Assign Partner to Outputs and budget in COMPASS
Create PPA Contract shell. Download and draft PW template
Upload PW to Cloud ERP for approval
Finalize and sign PW contract
Negotiate PW, Financial Plan, Results Plan & Risk Register
Create, negotiate, sign, & approve partnership agreements in Cloud-ERP (PFA & DPA)
Upload Partnership Framework Agreement (PFA) in Aconex
Upload Data Protection Agreement (DPA) (where required) in Aconex
Project Development
Monitoring
Partner Reports Results Periodically for UNHCR Validation
Partner Reports Financials (PFR) Periodically for UNHCR Verification
Project Performance Verification (PMC02) of Partner
Project Financial Verification (PMC03) of Partner
Raise Implementation Monitoring Issues in Aconex Field
Update Expenses in Cloud ERP
Register Digital PDF Copy of Certificate of Instalment
5
Amend Budget / Outputs/Indicators in COMPASS
Send COMPASS Partnership Scope to PROMS
Negotiation of Financial Plan and Results Plan Amendment
Project Workplan Contract Amendment in Cloud ERP
UNHCR ‘Cancel’ Project Financial Report (PFR)
Conduct Offline Quality Assurance Checks
Review Risk Register
6
Upload Project Workplan in Document Register
Generate Prepayment invoice in Cloud ERP (if necessary)
Upload the Signed Amendment Contract and approve it in Cloud ERP
UNHCR Representative 2nd Stage Approval of Financial Plan Amendment
Update Purchase Order in Cloud ERP
7
Partner transmits a “Request for Liquidation / Implementation Period” via Mail module
If ready, country operation sends request to RB for review / approval
UNHCR reviews request and requests more information if required
RB informs Country Operation of approval / rejection
Country Operation responds to partner’s request
Amendments
Exceptions
Validate and Release Subsequent Prepayment

## Slide 4
BIG PICTURE – PROMS FUNCTIONALITY
PROMS IN PRACTICE
PROMS
Other Systems
Audits and Closure
Commence project audit
8
Receive Response to Enquiry for Information
Submit Enquiry for Information via Mail module
Submit Request for Payment for unspent balances / audit recoveries
Receive Response
Verify Payment has been made in Cloud ERP
10
Submit Partner Agreement Closure Request via Mail module
Approval of Request
Update Status of Contract
Update Status of Partnership Agreement
11
Auditor uploads draft audit report
UNHCR uploads audit recommendations
Auditor transmits audit report to partner via a workflow
UNHCR transmits audit recommendations to partner via a workflow
9
Partner created as a “Supplier” in Cloud ERP and available in COMPASS
Partner registers in Aconex
Partner registration in UNPP
1
2
ICA in UNPP / PROMS
3
Create Purchase Order (PO)
Register digital PDF Copy of PO
Release Initial Instalment & Create, Validate & Release Prepayment Invoice
Register Digital PDF Copy of Certificate of Instalment
4
Complete final workflow step for Financial Plan and Results Plan respectively
Assign Partner to Outputs and budget in COMPASS
Create PPA Contract shell. Download and draft PW template
Upload PW to Cloud ERP for approval
Finalize and sign PW contract
Negotiate PW, Financial Plan, Results Plan & Risk Register
Create, negotiate, sign, & approve partnership agreements in Cloud-ERP (PFA & DPA)
Upload Partnership Framework Agreement (PFA) in Aconex
Upload Data Protection Agreement (DPA) (where required) in Aconex
Project Development
Monitoring
Partner Reports Results Periodically for UNHCR Validation
Partner Reports Financials (PFR) Periodically for UNHCR Verification
Project Performance Verification (PMC02) of Partner
Project Financial Verification (PMC03) of Partner
Raise Implementation Monitoring Issues in Aconex Field
Update Expenses in Cloud ERP
Register Digital PDF Copy of Certificate of Instalment
5
Amend Budget / Outputs/Indicators in COMPASS
Send COMPASS Partnership Scope to PROMS
Negotiation of Financial Plan and Results Plan Amendment
Project Workplan Contract Amendment in Cloud ERP
UNHCR ‘Cancel’ Project Financial Report (PFR)
Conduct Offline Quality Assurance Checks
Review Risk Register
6
Upload Project Workplan in Document Register
Generate Prepayment invoice in Cloud ERP (if necessary)
Upload the Signed Amendment Contract and approve it in Cloud ERP
UNHCR Representative 2nd Stage Approval of Financial Plan Amendment
Update Purchase Order in Cloud ERP
7
Partner transmits a “Request for Liquidation / Implementation Period” via Mail module
If ready, country operation sends request to RB for review / approval
UNHCR reviews request and requests more information if required
RB informs Country Operation of approval / rejection
Country Operation responds to partner’s request
Amendments
Exceptions
Validate and Release Subsequent Prepayment

## Slide 5
BIG PICTURE – PROMS FUNCTIONALITY
PROMS IN PRACTICE
PROMS
Other Systems
Partner created as a “Supplier” in Cloud ERP and available in COMPASS
Partner registers in Aconex
Partner registration in UNPP
1
2
ICA in UNPP / PROMS
3
Create Purchase Order (PO)
Register digital PDF Copy of PO
Release Initial Instalment & Create, Validate & Release Prepayment Invoice
Register Digital PDF Copy of Certificate of Instalment
4
Complete final workflow step for Financial Plan and Results Plan respectively
Assign Partner to Outputs and budget in COMPASS
Create PPA Contract shell. Download and draft PW template
Upload PW to Cloud ERP for approval
Finalize and sign PW contract
Negotiate PW, Financial Plan, Results Plan & Risk Register
Create, negotiate, sign, & approve partnership agreements in Cloud-ERP (PFA & DPA)
Upload Partnership Framework Agreement (PFA) in Aconex
Upload Data Protection Agreement (DPA) (where required) in Aconex
Project Development
Monitoring
Partner Reports Results Periodically for UNHCR Validation
Partner Reports Financials (PFR) Periodically for UNHCR Verification
Project Performance Verification (PMC02) of Partner
Project Financial Verification (PMC03) of Partner
Raise Implementation Monitoring Issues in Aconex Field
Update Expenses in Cloud ERP
Register Digital PDF Copy of Certificate of Instalment
5
Validate and Release Subsequent Prepayment

## Slide 6
IMPLEMENTATION MONITORING
PROMS IN PRACTICE
BUSINESS IMPACT
Introduction of field templates that are accessible on tablets and smartphones.
When short-comings / issues are identified, a task can be generated and assigned to the appropriate person / organization.
Issues can be recorded out in the field when offline and later automatically synced when online.
Ongoing monitoring reduces the dependency on scheduled, announced and formal MFT visits.
UNHCR
Partner
Integration
E-Mail
The assignee attaches documents, adds notes and updates the status with the relevant status (Dispute Issue if not in agreement with the issue or Mark Ready to Inspect if actions are taken).. The assignee can also edit in the issue and reassign it.
3
During the implementation monitoring, UNHCR or a partner (as an initiator) can raise a recommendation or an appreciation using Field “Issues” by selecting the “Issue” type “Implementation Monitoring”.
1
The partner or UNHCR, as the assignee (Field Administrator), receives a summary email notification at the end of the day that a recommended/appreciation action is assigned to their organization.
2
The initiator (Field Administrator) receives a summary email notification at the end of the day that action has been taken.
a) If the initiator is satisfied with the action taken, they close the “Issue”.
b) If the assignee does not agree with the recommendation, they can assign it to become “in dispute”.
4

## Slide 7
PROJECT FINANCIAL REPORT (PFR)
PROMS IN PRACTICE
The Project Financial Report (PFR) workflow is not only about the submission of the PFR template (despite the workflow name). It includes the submission of the project performance verification and project financial verification reports (PMC02 and PMC03 respectively).
The PFR workflow feeds into the process of documenting the partner’s overall performance to-date, taking into consideration:
  Reported progress against results,
  Expenditure to-date
  Action taken in follow-up on implementation monitoring recommendations,
  Progress against a partner’s PSEA Capacity Strengthening and Implementation plan,
  Feedback from people with and for whom the partner/UNHCR works,
  Progress against risk treatment plans and ICA/ICQ recommendations,
The PFR workflow therefore encompasses partner reporting and UNHCR's verification processes, documenting UNHCR’s implementation monitoring, and hence it is initiated by Programme with Project Control in copy from the start.
0
BUSINESS IMPACT
Standardized PFR templates
Partners can upload supporting documentation from their corporate systems to PROMS
Project control and auditors can more easily verify and reconcile financial plans and reporting
Real-time updates on agreement financial information

## Slide 8
PROJECT FINANCIAL REPORT (PFR): 1/7
PROMS IN PRACTICE
The partner receives an email notifying them of the workflow transmittal. The partner opens the workflow step, downloads the PFR template and enters expenditure, proposed reallocations/budget variations (if applicable) and the next proposed prepayment amount (if applicable). The partner uploads the modified excel file in the workflow step and completes the workflow step by selecting the review outcome of “Approved”.
3
The PFR template is generated in Aconex via integration and is based on the contents of the final approved financial plan (for the first PFR) or it is based on the previous approved PFR (if not the PFR). The document will have a status of “Not Started”, revision number of 0 and version number of 1.
1
UNHCR Programme selects the PFR template from the Aconex Document Register and transmits it on a workflow to the partner, using the “Project Financial Report Submission” workflow template. When editing the workflow settings, Programme adds Project Control to be in copy for the first step (“Partner PFR Input”).
2
UNHCR Programme & Project Control receive an email notification of the workflow transmittal. Project Control can download the partner-completed PFR from the transmittal and commence their financial verification. UNHCR Programme will download the partner-completed PFR from the workflow step.
4
UNHCR
Partner
Integration
E-Mail

## Slide 9
PROJECT FINANCIAL REPORT (PFR): 2/7
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
If there are no concerns with the partner-completed PFR, Programme can complete the workflow step by selecting the review outcome of “Agreed” without uploading a replacement file for the partner-completed PFR, and simply attaching the PMC02 PDF as the supplementary file. If there is no need for UNHCR Programme to complete and upload the PMC02, they can complete the workflow step by selecting the status “Review Not Required” without uploading a replacement file for the partner-completed PFR.
7
UNHCR Programme completes the Project Performance Verification as a desk-review and fills out the PMC02 form via Field Inspections, obtaining the partner’s acceptance status and their signature.
5
Once the PMC02 is completed and signed by both parties, UNHCR Programme downloads the closed PMC02 form as a PDF and uploads it into the “1st Stage Approval” step of the PFR workflow as a supplementary file.
6

## Slide 10
PROJECT FINANCIAL REPORT (PFR): 3/7
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
If the partner selects “Revise & Resubmit", UNHCR Programme can initiate another new “Partner Sub Workflow” until there is an agreement on the partner-completed PFR.
10
8
For the sub workflow single step, the partner selects the review outcome of either “Proceed”, if in agreement with UNHCR’s requested changes/review, or “Revise & Resubmit” if the partner does not agree with the proposal from UNHCR Programme.
9
Once agreement is met with the partner, the use of the sub workflow process ends, and Programme uploads the final partner-completed PFR to the parent “1st Stage Approval” workflow step and completes “1st stage approval” step by selecting the review outcome of “Approved”.
11
UNHCR Programme may transmit the partner-completed PFR on a “Partner Sub Workflow” if Programme identifies concerns with the PFR and the corrections can be made within the workflow step’s deadline. The concerns are outlined in the "workflow note" box in the workflow wizard when initiating the Partner Sub Workflow.
0

## Slide 11
PROJECT FINANCIAL REPORT (PFR): 4/7
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
Once the PMC03 is completed and signed by all parties, UNHCR Project Control downloads the closed PMC03 form as a PDF and uploads it into the “2nd Stage Approval” step of the workflow as a supplementary file.
14
12
UNHCR Project Control completes the Project Financial Verification PMC03 form with the partner via Field Inspections, obtains the UNHCR approval signature (from the most senior UNHCR project control focal point), and the partner’s acceptance status and signature.
13
UNHCR Project Control receives an email notification of the workflow transmittal. UNHCR Project Control opens the workflow in the “2nd Stage Approval” step and downloads the partner-completed PFR and PMC02 (if applicable).

## Slide 12
PROJECT FINANCIAL REPORT (PFR): 5/7
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
If the partner selects “Revise & Resubmit", UNHCR can initiate another new “Partner Sub Workflow” until there is an agreement on the PFR. Once agreement is met with the partner, the use of the sub workflow process ends and returns to the parent “2nd Stage Approval” step.
17
15
UNHCR Project Control may transmit the UNHCR-completed PFR on a “Partner Sub Workflow” to reach agreement with the partner, if this can be completed within the workflow step’s deadline. The partner selects either “Proceed”, if in agreement with UNHCR’s changes or “Revise & Resubmit” if the partner does not agree with the proposal from UNHCR Project Control.
16
UNHCR Project Control uploads the partner-agreed UNHCR-completed PFR in the “2nd Stage Approval” workflow step, completes the workflow step with the review outcome of “Approved”, and moves it to the “3rd Stage Approval” step.
18
UNHCR Project Control enters the verified expenditures, proposed reallocations/budget variations (if applicable) and the proposed next prepayment value (if applicable) into the partner-completed PFR to become the UNHCR-completed PFR.

## Slide 13
PROJECT FINANCIAL REPORT (PFR): 6/7
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
19
If in agreement with the PFR, the UNHCR Representative approves it by completing the workflow step with the review outcome of “Approved”. The workflow ends, the PFR has been approved, the creation of the next prepayment invoice is triggered in Cloud ERP (if applicable) and the next PFR template is generated in PROMS.
20
The UNHCR Representative (or delegated authority) receives an email notification of the workflow transmittal. The UNHCR Representative opens the workflow in the “3rd Stage Approval” step, downloads the PFR and reviews the content.

## Slide 14
PROJECT FINANCIAL REPORT (PFR): 7/7
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
(ii) Partner Review: The partner then receives the modified PFR and, if accepts, updates the PFR and selects the review outcome of “Proceed”. If the partner contests the changes, then they enter their comments in the PFR and select “Revise and Resubmit”.
23
21
(i) UNHCR Programme Review: UNHCR Project Control downloads the PFR and reviews the Representative’s workflow note, addresses the concerns, uploads the modified PFR in the sub workflow and selects the review outcome of “Proceed”.
22
(iii) UNHCR Programme Approval: UNHCR Project Control reviews the PFR from the partner and, if in agreement, finalizes the PFR. If not in agreement, the Representative Sub Workflow can be restarted and continue until agreement is met with the Partner. Once agreed, the Sub Workflow ends and returns to the parent “3rd Stage Approval” workflow step (return to step 19).
24
If modifications are required and can be achieved within the workflow step’s deadline, the Representative transmits the PFR on a “Representative Sub Workflow”, adding a workflow note in the workflow wizard, which comprises the following steps:
(i) UNHCR Programme Review; (ii) Partner Review; (iii) UNHCR Programme Approval.

## Slide 15
PROJECT PERFORMANCE VERIFICATION (PMC02) – 1/2
PROMS IN PRACTICE
If required, UNHCR can create an “Issue” for a particular question and assign it to the partner. The partner would then need to respond to the assigned Issues. After the questions are answered, UNHCR Programme adds their name, title and signature to the form.
3
1
UNHCR Programme answers the questions in the PMC02 form, attaching any supporting documents, such as the issues report, results reports, feedback from the supported community For the ‘Comments on Implementation Process’ section, UNHCR Programme attaches evidence of results reported to-date.
2
UNHCR assigns the completed PMC02 form to the partner for their review with a set due date. The partner (Field Administrator) receives a summary notification email at the end of the day on the assigned PMC02 from UNHCR.
4
UNHCR
Partner
Integration
E-Mail
UNHCR Programme creates a new Field “Inspection” using the PMC02 form and downloads the report of implementation monitoring issues awaiting action (i.e. “ready to inspect”, “open” and “in dispute”). Programme also gathers evidence of results reported to-date (Activity Info, KOBO, excel sheet etc.).
BUSINESS IMPACT
Ongoing monitoring will reduce dependency on scheduled, announced, formal MFT visits
Field checklists accessible from tablets and smartphones (can be carried out in the field when off-line and automatically synced when on-line)
When short-comings / issues are identified, a task can be generated and assigned to the appropriate person / organization
Partners can upload supporting documentation from their corporate systems to PROMS

## Slide 16
PROJECT PERFORMANCE VERIFICATION (PMC02) – 2/2
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
BUSINESS IMPACT
Ongoing monitoring will reduce dependency on scheduled, announced, formal MFT visits
Field checklists accessible from tablets and smartphones (can be carried out in the field when off-line and automatically synced when on-line)
When short-comings / issues are identified, a task can be generated and assigned to the appropriate person / organization
Partners can upload supporting documentation from their corporate systems to PROMS
If in agreement with the content of the modified PMC02 and no further input is required, the partner selects the “Acceptance” status, enters their signature and reassigns the form to UNHCR, setting a due date for UNHCR if desired.
7
5
If the partner has not accepted the PMC02 form and not added their signature, UNHCR Programme may choose to modify the answers to reflect the partner’s comments. UNHCR reassigns the modified PMC02 form to the partner for their review, setting a due date for the partner (return to step 5).
6
UNHCR checks that the % of completion of the form is 100% and then closes the form, completing the PMC02.
8
The partner reviews the information in the PMC02 form and can create an Issue for a particular question, assigning it to UNHCR. The partner can also add notes and/or attachments to any question. The partner can select an option for the Acceptance Status, add their name, title and signature, and then assign the PMC02 to UNHCR, setting a due date for UNHCR if desired.

## Slide 17
PROJECT FINANCIAL VERIFICATION (PMC03) – 1/3
PROMS IN PRACTICE
If required, UNHCR can create an “Issue” for a particular question and assign it to the partner. The partner would then need to respond to the assigned Issue. Equally, the partner can also create an Issue for a particular question to assign to UNHCR (see slide 28).
3
1
UNHCR Project Control answers the questions in the PMC03 form jointly while onsite/in the office of the partner. UNHCR Project Control may upload supporting documentation (as applicable) and/or enter additional notes for a question.
2
UNHCR Project Control adds their name, title and signature to the PMC03 form and then assigns it internally to the UNHCR approver (most senior Project Control focal point in the operation) with a due date for their signature.
4
UNHCR
Partner
Integration
E-Mail
During the Project Financial Verification, UNHCR Project Control creates a new Field “Inspection” using the PMC03 form and conducts the financial verification with the partner.
BUSINESS IMPACT
Ongoing monitoring will reduce dependency on scheduled, announced, formal MFT visits
Field checklists accessible from tablets and smartphones (can be carried out in the field when off-line and automatically synced when on-line)
When short-comings / issues are identified, a task can be generated and assigned to the appropriate person / organization
Partners can upload supporting documentation from their corporate systems to PROMS

## Slide 18
PROJECT FINANCIAL VERIFICATION (PMC03) – 2/3
PROMS IN PRACTICE
The partner reviews the information in the PMC03 form and can create an Issue for a particular question and assign it to UNHCR, as well as add notes and/or attachments to any question. The partner can select an option for the Acceptance Status, add their name, title and signature, and then assign the PMC03 to UNHCR, setting a due date for UNHCR if desired.
7
5
The UNHCR approver assigns the completed and signed PMC03 form to the partner for their review, setting a due date for the partner. The partner (Field Administrator) receives a summary notification email at the end of the day on the assigned PMC03 from UNHCR.
6
If the partner has not accepted the PMC03 form, UNHCR Project Control may choose to modify the answers to reflect the partner’s comments. UNHCR reassigns the modified PMC03 form to the partner for their review.
8
UNHCR
Partner
Integration
E-Mail
The UNHCR approver reviews the PMC03 form and adds their name, title and signature for internal approval.
BUSINESS IMPACT
Ongoing monitoring will reduce dependency on scheduled, announced, formal MFT visits
Field checklists accessible from tablets and smartphones (can be carried out in the field when off-line and automatically synced when on-line)
When short-comings / issues are identified, a task can be generated and assigned to the appropriate person / organization
Partners can upload supporting documentation from their corporate systems to PROMS

## Slide 19
PROJECT FINANCIAL VERIFICATION (PMC03) - 3/3
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
BUSINESS IMPACT
Ongoing monitoring will reduce dependency on scheduled, announced, formal MFT visits
Field checklists accessible from tablets and smartphones (can be carried out in the field when off-line and automatically synced when on-line)
When short-comings / issues are identified, a task can be generated and assigned to the appropriate person / organization
Partners can upload supporting documentation from their corporate systems to PROMS
9
UNHCR checks that the % of completion of the form is 100% and then closes the form, completing the PMC03.
10
If in agreement with the content of the PMC03 and no further input is required, the partner selects the “Acceptance” status, enters their signature and reassigns the form to UNHCR, setting a due date for UNHCR if desired.

## Slide 20
BIG PICTURE – PROMS FUNCTIONALITY
PROMS IN PRACTICE
PROMS
Other Systems
Partner created as a “Supplier” in Cloud ERP and available in COMPASS
Partner registers in Aconex
Partner registration in UNPP
1
2
ICA in UNPP / PROMS
3
Create Purchase Order (PO)
Register digital PDF Copy of PO
Release Initial Instalment & Create, Validate & Release Prepayment Invoice
Register Digital PDF Copy of Certificate of Instalment
4
Complete final workflow step for Financial Plan and Results Plan respectively
Assign Partner to Outputs and budget in COMPASS
Create PPA Contract shell. Download and draft PW template
Upload PW to Cloud ERP for approval
Finalize and sign PW contract
Negotiate PW, Financial Plan, Results Plan & Risk Register
Create, negotiate, sign, & approve partnership agreements in Cloud-ERP (PFA & DPA)
Upload Partnership Framework Agreement (PFA) in Aconex
Upload Data Protection Agreement (DPA) (where required) in Aconex
Project Development
Monitoring
Partner Reports Results Periodically for UNHCR Validation
Partner Reports Financials (PFR) Periodically for UNHCR Verification
Project Performance Verification (PMC02) of Partner
Project Financial Verification (PMC03) of Partner
Raise Implementation Monitoring Issues in Aconex Field
Update Expenses in Cloud ERP
Register Digital PDF Copy of Certificate of Instalment
5
Amend Budget / Outputs/Indicators in COMPASS
Send COMPASS Partnership Scope to PROMS
Negotiation of Financial Plan and Results Plan Amendment
Project Workplan Contract Amendment in Cloud ERP
UNHCR ‘Cancel’ Project Financial Report (PFR)
Conduct Offline Quality Assurance Checks
Review Risk Register
6
Upload Project Workplan in Document Register
Generate Prepayment invoice in Cloud ERP (if necessary)
Upload the Signed Amendment Contract and approve it in Cloud ERP
UNHCR Representative 2nd Stage Approval of Financial Plan Amendment
Update Purchase Order in Cloud ERP
Amendments
Validate and Release Subsequent Prepayment

## Slide 21
AMENDMENTS
PROMS IN PRACTICE
To re-open COMPASS to amend the partner’s budget and/or outputs/indicators, the status of the current PFR needs to be changed to “cancelled” according to:
If the document status of the PFR is “not started,” update the document and change the status to ‘cancelled’.
OR: If the PFR has already been transmitted on a workflow that is in progress, the current/pending workflow step needs to be with UNHCR to change the “Review Outcome” to be ‘cancelled’. If the current/pending step is with the partner, UNHCR can either:
  ‘skip’ the partner step from the workflow, so that the current/pending step moves on to UNHCR for action, then UNHCR selects “cancelled” for the “Review Outcome”. Once the workflow is cancelled, no further action is required, OR:
  ‘terminate’ the workflow, then update the document and change its status to “cancelled” from the Document Register.
  Note: Terminating a workflow alone does not cancel a document in PROMS document register.
BUSINESS IMPACT
Integration between COMPASS and PROMS to upload budget envelope (by output and implementer) in PROMS document register
Partner agreements with simpler project descriptions and financial plans
Document management functionality to enable version control and clear audit trails
Workflow functionality to facilitate partner collaboration and electronic budget approval process

## Slide 22
BUDGET / RESULT PLAN AMENDMENTS IN COMPASS
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
UNHCR sends the partnership scope to PROMS to begin amendment negotiation in PROMS.
3
To re-open COMPASS to amend the partner’s budget and/or outputs/indicators, UNHCR needs to change the document status of the current PFR to ‘Cancelled’.
1
UNHCR applies budget and/or results changes in COMPASS.
2
The existing Financial and Results Plan are automatically updated as new files in the Aconex Document Register with a new Revision number and the status of “not started”
4

## Slide 23
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
FINANCIAL PLAN AMENDMENT - 1ST STAGE APPROVAL (PROMS) – 1/2
The partner receives an email notification of the workflow transmittal, opens the workflow step and downloads the financial plan amendment template. The partner enters proposed amended budget and requested next prepayment value (if applicable), as well as comments and reference codes (if necessary). The partner uploads the proposed financial plan amendment in the “Partner Financial Plan Proposal” workflow step and completes the workflow step by selecting the review outcome of “Agreed”.
2
UNHCR Programme initiates a workflow using the “Negotiation of Financial Plan” workflow template and transmits the financial plan amendment template to the partner.
1

## Slide 24
FINANCIAL PLAN AMENDMENT - 1ST STAGE APPROVAL (PROMS) – 2/2
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
The partner selects either “proceed”, if in agreement with UNHCR’s changes, or “revise & resubmit” if not in agreement with UNHCR proposal (process then continues until there is an agreement on the financial plan). Once agreed, the Sub Workflow ends and returns to the parent “1st Stage Approval” workflow step.
5
UNHCR Programme receives an email notification of the workflow transmittal, opens the workflow step, downloads the partner-proposed financial plan amendment and reviews the proposed amended budget. UNHCR Programme adds any “general agreement comments”, populates the “UNHCR proposed value” column and enters the approved prepayment (if applicable).
3
If not in agreement with the partner’s proposal and the negotiation can be completed within the workflow step’s deadline, UNHCR Programme transmits the proposed financial plan amendment on a “Partner Sub Workflow”.
4
UNHCR Programme uploads the partner-agreed financial plan amendment in the “1st Stage Approval” workflow step and completes the workflow step with the review outcome of “agreed.” The workflow moves to the “2nd Stage Approval” step.
6

## Slide 25
KEY NOTES – FINANCIAL PLAN AMENDMENT 1ST STAGE APPROVAL
PROMS IN PRACTICE
Keep in mind: The “positive” column in the Financial Plan amendment template is used to reflect an increase in budget value, and the “negative” column is used to reflect any decrease in the budget value.
The same rules when dealing with the Financial Plan excel apply to this amendment template, including not changing the file name, type, author, formatting or the protection of the document, as well as not to enter extra decimals (beyond what is permissible for the currency), commas or formulas.
Partners MUST NOT alter the last received prepayment row in any way, for example, where the 1st prepayment amount has been released, any top-up prepayment then becomes the 2nd prepayment amount that must be entered in the 2nd prepayment row.

## Slide 26
AMEND PROJECT WORKPLAN CONTRACT (CLOUD ERP) – 1/2
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
UNHCR Programme amends the Project Workplan, editing only the required text and changes the ‘version’ status within the Project Workplan.
Note: UNHCR must change status to 01 for amendment #1 (or 02 for amendment #2 etc.). In case text is no longer required – UNHCR simply deletes the text (the initial contract remains in Cloud ERP as a reference for audit trail).
3
UNHCR Programme finds and opens the existing Project Workplan in Cloud ERP Contracts Module and selects “Amend” under the drop-down menu for ‘Actions’. UNHCR Programme selects “Version the Contract.”
1
UNHCR Programme navigates to Contract Terms and, under ‘Terms Actions’, selects ‘Download Contract’.
2
UNHCR Programme uploads the draft amended project workplan contract (as a word document) to the Document Register and transmits it to the partner via the “Formal Partner review” workflow for negotiation / agreement.
Note: In case details are amended by UNHCR only, i.e. the project end-date that is already agreed with the partner, the draft does not need to be transmitted to the partner via a workflow.
4

## Slide 27
AMEND PROJECT WORKPLAN CONTRACT (CLOUD ERP) – 2/2
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
UNHCR sends the amended project workplan contract to all parties for signature. Once signed, the contract is uploaded into Cloud ERP as a PDF under “contract documents” and UNHCR Programme submits the project workplan contract to the ‘Approver’ (as delegated by the Representative) for approval. The signatory information is entered in Cloud ERP and UNHCR Programme checks that the contract has an 'Active' status.
7
5
Conduct Quality Assurance: An amendment requires that UNHCR Project Control reviews the agreement. Therefore, Project Control reviews the final project workplan documents and completes the Quality Assurance Checklist.
6
Review Risk Register: UNHCR Programme considers any changes or updates required to the Risk Register and actions accordingly. Changes to the Risk Register are updated in the Document Register.
Note: If any risks are added/deleted, the total number of risks for the affected category(ies) needs to be updated in the Risk Register.

## Slide 28
FINANCIAL PLAN AMENDMENT - 2ND STAGE APPROVAL (PROMS) – 1/2
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
(i) UNHCR Programme Review: UNHCR Programme reviews the Representative’s workflow note addresses the concerns, uploads the modified financial plan in the sub workflow and selects “proceed”.
3
The UNHCR Representative receives an email notification of the workflow transmittal, opens the workflow step, downloads the financial plan amendment and reviews the content. If in agreement with the financial plan amendment, the UNHCR Representative approves it by completing the workflow step with the review outcome of “agreed”. The workflow ends and the financial plan amendment has been approved.
1
If modifications are required and can be achieved within the workflow step’s deadline, the Representative transmits the financial plan amendment on a “Representative Sub Workflow”, adding a workflow note in the workflow wizard.
2

## Slide 29
FINANCIAL PLAN AMENDMENT - 2ND STAGE APPROVAL (PROMS) – 2/2
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
The Representative’s approval triggers the updated purchase order in Cloud ERP, and its PDF copy in Aconex, the subsequent prepayment invoice in Cloud ERP (if applicable) and the generation of the next project financial report (PFR). Once the prepayment invoice is validated and released, the new Certificate of Instalment is created in Aconex. Once the integration is completed in Aconex, the negotiated budget is reflected in COMPASS.
6
(ii) Partner Review: The partner then receives the modified financial plan amendment and, if accepts, updates it and selects “proceed”. If the partner contests the changes, then they enter their comments in the financial plan amendment and select “revise and resubmit”.
4
(iii) UNHCR Programme Approval: UNHCR Programme reviews the financial plan amendment and, if in agreement, finalizes it and selects “proceed”. If UNHCR Programme is not in agreement with partner’s comments, they start a “Partner Sub Workflow” and the process continues until both parties agree on content. Once agreed, the Sub Workflow ends and returns to the parent “2nd Stage Approval” workflow step.
5
The amended financial plan is used to update the cost worksheet, contract and contract line items in “Connected Cost”. This information is populated in “Connected Cost” via the integration.
7

## Slide 30
AMEND RESULTS PLAN (PROMS) – 1/2
PROMS IN PRACTICE
The Partner receives an email notification of the workflow transmittal, opens the workflow step and downloads the results plan template. The partner enters the indicator targets and adds any additional indicators to its separate sheet (if applicable). The partner uploads the amended results plan into the workflow step and completes it by selecting the appropriate review outcome.
3
The amended Results Plan is automatically registered in the Aconex Document Register with a new revision number, the status of “not started” and updated information from COMPASS via integration.
Note: any indicators previously entered in the Additional Indicators tab will be automatically deleted. UNHCR and the partner will need to re-insert them again in the Additional Indicator tab.
1
UNHCR Programme selects the Results Plan Excel template from the Aconex Document Register and transmits it on a workflow by selecting the “Negotiation of Indicators” workflow template.
2
UNHCR Programme receives an email notification of the workflow transmittal and downloads the file and reviews the partner’s inputs, including the additional indicators.
4
UNHCR
Partner
Integration
E-Mail

## Slide 31
AMEND RESULTS PLAN (PROMS) – 2/2
PROMS IN PRACTICE
UNHCR
Partner
Integration
E-Mail
If there is agreement on the targets, UNHCR will enter the same targets in their required fields, UNHCR Programme enters the same targets in their required fields and uploads the final agreed results plan into the workflow step, selecting the review outcome of “Agreed”. The results plan is approved. After the integration is completed for both the FPN and IND files, the agreed targets will be reflected to COMPASS.
6
If a revision is required and can be completed with the workflow step’s deadline, UNHCR Programme enters the UNHCR Proposed Numerators & Proposed Denominators and then transmits the modified results plan on a “Partner Sub Workflow” (this process continues until UNHCR and Partner agrees on the targets).
5

## Slide 32
Q&A