## Guidance
PROJECT PERFORMANCE VERIFICATION REPORT- PMC02
Guidance on how to answer each question in the form |  |  | Note: Questions with * are mandatory.
The PMC02 UNHCR preparer finds the correct Field Inspections PMC02 form. The UNHCR preparer will "Start" & complete questions 1-21 within the PMC02 form, attaching supporting documentation to a particular question where available, and signing when complete. The UNHCR preparer then assigns the PMC02 to the Partner Organization, entering a Due Date for their review and signature. The Partner Administrator receives the PMC02 (via an email summary) and can assign it to a colleague. The partner adds notes and/or completes questions 22-25, before assigning the PMC02 back to UNHCR. UNHCR can edit based on Partner's notes and supporting evidence, and assign back to the partner (as required) before UNHCR 'closes' the status of the PMC02. The most senior member of Programme will conduct the final review of the PMC02, before downloading it as a PDF and uploading it to the PFR workflow as a supplementary file for the 1st stage approval step. In case any changes are required, UNHCR can reopen the PMC02 for editing at any time.
Grant agreements - a monitoring report is no longer required from the partner. Instead, UNHCR and the grant agreement partner will complete a PMC02 to document all supporting evidence of the activity/activities implemented. Therefore, it is expected that the UNHCR preparer will select the answer 'No' for many of the mandatory fields below for grant agreement PMC02 completion, without raising any issues.
KEY | Question for UNHCR to firstly provide a response
Question for partner to firstly proivde a reponse
TOPIC | PRELIMINARY INFORMATION
Q # | Question | Type of Answer | Guidance
1 | Implementer* | Free text | Write out the full name of the partner. Make sure you copy and paste the exact name of the partner from the Document Register. However, since this PMC02 will be attached to the PFR workflow in Aconex, you will be able to easily find the documentation via the implementer associated with the PFR.
2 | Partner Agreement / Contract* | Free text | Enter the Cloud ERP Contract ID # for the partnership agreement. i.e. Cost Centre + Y + last two digits of year + M (for migrated partner record) or P (new partner record) + Partner Supplier Number (last six digits). Make sure you copy and past the exact contract number from the Document Register. However, since this PMC02 will be attached to the PFR workflow in Aconex, you will be able to easily find the documentation via the implementer associated with the PFR.
3 | The partner has closed all or has no implementation monitoring recommendations awaiting action (awaiting action includes “Ready to Inspect,” ‘Open’ or "In Dispute" under Implementation Monitoring issues)* | Yes / No | This is related to any Field Issues raised by UNHCR for the partner's action. Check the Field Issues raised for this partner. You can generate a report from Aconex on all issues, and filter, as neccessary, by "Assigned by", "Assigned to", or by 'Status' or by other parameters. Answer 'Yes' or 'No.' Attach the downloaded Field/Issues report as supporting evidence. In case there are no Field Issues for this partner in Aconex and/or the partner is not yet onboarded within Aconex - you can enter 'No'.
4 | UNHCR has closed all or has no implementation monitoring recommendations awaiting action, under this partnership?* | Yes / No | This is related to any Field Issues raised by the partner for UNHCR's action. Check the Field Issues raised by this partner. You can generate a report from Aconex on all issues, and filter, as neccessary, to narrow your search. Answer 'Yes' or 'No.' You only need to download and attach the Field/Issues report once per PMC02. In case there are no Field Issues for UNHCR in Aconex and/or the partner is not yet onboarded within Aconex - you can enter 'No'.
TOPIC | PROTECTION AND SOLUTIONS
Q # | Question | Type of Answer | Guidance
5 | The partner has closed or has no protection and solutions challenges, including implementation monitoring recommendations awaiting action?* | Yes / No | Check any Field Issues raised by UNHCR for the partner's action related to Protection and solution category and select 'Yes' if there are pending issues, otherwise select 'No.' In case there are no Field Issues for this partner in Aconex and/or the partner is not yet onboarded within Aconex - you can enter 'No'.
6 | Additional protection challenges are identified (If ‘Yes’ - open "Implementation Monitoring" issue)?* | Yes / No | Discuss with protection colleagues. Are there protection challenages raised during continuous monitoring via reports, emails and/or meetings with partners that are pending action not documeted in Aconex? Please check with your operation's focal point surrounding any feedback, referrals and/or complaints raised by forcibly displaced and stateless people and/or the community where our partner is working. Are there pending matters for UNHCR/partner reponse in regards to this project? In case there are such matters, it is important to open an issue for the partner to follow-up.
TOPIC | CONSTRUCTION AND INFRASTRUCTURE
Q # | Question | Type of Answer | Guidance
7 | The partner has closed all or has no construction and infrastructure challenges, including implementation monitoring recommendations awaiting action? | Yes / No | This section is only applicable to projects surrounding construction and infrastructure. If not applicable, move on to the next section starting from Q10. Check any Field Issues raised by UNHCR for the partner's action related to the construction and infrastructure category and select 'Yes' if there are pending issues or otherwise select 'No.' In case there are no Field Issues for this partner in Aconex and/or the partner is not yet onboarded within Aconex - you can enter 'No'.
8 | The partner is applying a project management approach through the use of standardized construction templates? | Yes / No | Select 'Yes' if the partner is using a project management approach whereby there is evidence of clear control over and methodical documentation of the construction/infrastructure activities in terms of quality, financial and time management. This may include good practice templates for managing the construction/infrastructure project, such as templates for site meeting minutes, progress reports, site instructions, a site monitoring checklist and a material approval request. You may attach samples of the partner's completed project management templates as evidence, as well as any other relevant project management documentation (e.g. email chains and photos). In case no such project management approach is evident, select 'No' and consult with the partner to sensitize them on project management processes and to share good practice templates. Raise an issue for the partner to follow-up on recommendations.
9 | Additional construction and infrastructure challenges are identified? (If ‘Yes’ - open "Implementation Monitoring" issue) | Yes / No | Discuss with your results managers/focal point/or field-based colleagues who are physically monitoring the construction and infrastructure project. Does the partner have any pending recommendations or challenges that are delaying implementation and are not documented in Aconex? Have adjustments to the project been made due to such challenges? Attach relevant meeting minutes, emails or monitoring reports as supporting evidence. In case there are further construction and infrastructure challenges, it is important to: 1. Discuss the matter with the partner and determine the root causes of the challenges, as well as an appropriate course of action to address them. 2. If the partner is not implementing a project management approach, sensitize them on project management processes and share good practice templates. 3. Raise an issue, under the construction and infrastructure category, for the partner to follow-up.
TOPIC | OPERATIONAL CONTEXT
Q # | Question | Type of Answer | Guidance
10 | The partner has closed or has no operational challenges raised, including implementation monitoring recommendations awaiting action?* | Yes / No / N/A | Check any Field Issues raised by UNHCR for the partner's action related to Operational context category and select 'Yes' if there are pending issues, otherwise select 'No.' In case there are no Field Issues for this partner in Aconex and/or the partner is not yet onboarded within Aconex - you can enter 'No'.
11 | Additional operational challenges are identified? (If ‘Yes’ - open "Implementation Monitoring" issue)* | Yes / No / N/A | The question is left for the partner to respond: You ask the partner to enter details here to provide a concise summary of any changes, variations or amendments from the original plan, and the circumstances or factors that prompted them. This might include changes resulting from individuals and/or community feedback, operational challenges or other constraints/opportunities encountered that required adapting the planned activities. In case there are further operational challenges identified by the partner and/or UNHCR during the project performance verification, select 'yes.' It is important to open an issue for follow-up. In case there are no additional operational challenges identified when completing this project performance verification, select 'No'. In case operational challenges are not appliable to the nature of the project activities (i.e. a research paper is the deliverable) you may select 'N/A.'
TOPIC | RISK MITIGATION MEASURES
Q # | Question | Type of Answer | Guidance
12 | The Risk Register (document form) has treatments past due date or there are serious concerns about the successful implementation of treatments? (if yes - open " implementation monitoring" issue and explain the risk and treatments to be actioned)* | Yes / No | Discuss with your Project Control colleagues. Check the Risk Register, the treatment plans and their due dates. In case there are overdue dates for any of the treatments and/or serious concerns about the successful implementation of treatments, then select 'Yes' and alert Project Control colleagues that the Risk Register may require a review and update by the partner.
13 | The Risk Register (document form) requires revision? (if yes –initiate a workflow to revise and resubmit the Risk Register)* | Yes / No | Select 'Yes', if there is a need to revise the Risk Register from the Document Register, otherwise, select 'No.' Project control may wish to share via the 'Formal Partner Review' workflow, for a joint review, informing Programme of any updates.
TOPIC | PROCUREMENT
Q # | Question | Type of Answer | Guidance
14 | Additional procurement challenges are identified? (If ‘Yes’ - open "Implementation Monitoring" issue to follow up) | Yes / No | Discuss with your Supply colleagues. If the partner's ICA/Q resulted in a high procurement risk-rating, this section is mandatory. Supply to advise as to whether procurement recommendations were followed-up to-date by the partner resulting from ICA/Q and/or financial verifications. If not, select 'No' and discuss with the partner; and/or raise an issue for the partner to follow-up. In case of no action has been taken by the partner (with high ICA/Q procurement risk-rating) supply colleagues will advise the IPMC in case further action and/or limitations are to be applied to the project workplan.
15 | Partner has closed all or has no procurement challenges, including implementation monitoring recommendations awaiting action? | Yes / No | Check any Field Issues raised by UNHCR for the partner's action related to Procurement category and select 'Yes' if there are pending issues, otherwise select 'No.'
TOPIC | STRENGTHENED PSEA MEASURES
Q # | Question | Type of Answer | Guidance
16 | The partner has undertaken progress towards their PSEA Capacity Strengthening Implementation Plan? (N/A if partners have full PSEA capacity)* | Drop-down menu choice: - No - Partially - Fully - N/A | In case the partner does not encounter forcibly displaced and/or stateless persons please select 'N/A.' Discuss with the operation's PSEA focal point. The focal point should check the PSEA Module in the UNPP and the status of implementing the Capacity Strengthening Implementation Plan (CSIP). Check if the partner has completed the planned activities within the 6 months or whether the partner requires an extension of 3 more months. - Select 'No' if the partner appears to not have made any progress towards their CSIP activities according to the due dates. Raise an issue for the partner's immediate attention and follow-up on their CSIP activities. - Select 'Partially' in case there has been partial progress towards their CSIP according to the due dates. - Select 'Fully' if there has been progress towards the CSIP, which results in the partner now obtaining full PSEA capacity. - Select 'N/A' if the partner does not encounter forcibly displaced and/or stateless persons OR if the partner has obtained full PSEA capacity.
TOPIC | notes ON IMPLEMENTATION PROCESS
Q # | Question | Type of Answer | Guidance
17 | Implementation is proceeding as planned towards indicator targets? Attach evidence of partner’s reported actuals against planned output indicators (If ‘No’ - open "Implementation Monitoring" issue)* | Drop-down menu choice: - Yes - Yes - with agreed minor adjustments - No | Discuss with the relevant Results Manager/s. Check if the partner's latest reported results (actuals) been validate. A partner reports to UNHCR on the agreed indicators, in accordance with the indicator reporting frequency and through the data collection system or tool stipulated in the project workplan. Once a partner reports on its indicators, the results manager checks the actual performance against the reported indicator values to validate what was reported. It is better if results are reported before the Project Financial Report (PFR) is shared to help with timely verifications. In case of recommendations and/or challenges and/or delays in progress, raise an issue.
18 | Record the most recently recorded progress towards each planned indicator - as a percentage (each indicator progress % = each indicator total target divided by latest reported actual, where relevant)* | Free text | List the indicators and calculate the implementation percentage using the latest reported actuals against the total target, noting on progress. This will be reviewed by Project Control when completing the PMC03. A copy of the validated indicator dataset (e.g. an extract from ActivityInfo or an Excel table) is uploaded here as supporting evidence.
19 | Any Other Observations/Remarks | Free text
TOPIC | PREPARED AND SIGNED BY UNHCR
Q # | Question | Type of Answer | Guidance
20 | Name, Title* | Free text | Name of the Programme colleague who is the PMC02 preparer.
21 | Signature* | Free text and Upload Signature: - Draw with mouse - Upload image file | Enter your name and electronically sign the PMC02.
TOPIC | PREPARED AND SIGNED BY PARTNER: OTHER (IF AVAILABLE)
Q # | Question | Type of Answer | Guidance
22 | Partner Acceptance Status | Drop-down menu choice: - Accepted - Accepted with notes - Not Accepted | The partner selects one of the drop-down options, reflecting their acceptance of the project performance verification.
23 | Partner notes | Free text | The partner may add further notes, and or add supporting evidence/documentation and/or raise additional issues as and where relevant in the above sections.
24 | Name, Title | Free text | Name of the reviewer from the partner's side.
25 | Signature | Free text and Upload Signature: - Draw with mouse - Upload image file | The partner enters their name and electronically signs the PMC02.

## Sample
PROJECT PERFORMANCE VERIFICATION REPORT- PMC02
Example of a pre-populated PMC02 for reference |  | Note: Questions with * are mandatory.
KEY | Question for UNHCR to firstly provide a response
Question for partner to firstly proivde a reponse
TOPIC | PRELIMINARY INFORMATION
Q # | Question | Response by UNHCR | Response by Partner
1 | Implementer* | Save the Children International (SCI)
2 | Partner Agreement / Contract* | 12345Y24M654321
3 | The partner has closed all or has no implementation monitoring recommendations awaiting action (awaiting action includes “Ready to Inspect,” ‘Open’ or "In Dispute" under Implementation Monitoring issues)* | No Attachments: UNHCR preparer attaches the Field/Issues generated report as supporting evidence. | Note: CSI has 2 'Open' issues and 1 "In Dispute." CSI colleagues are following up to now close the 2 open issues asap, within the due dates. CSI kindly requests a meeting with UNHCR on the issue in dispute to help find a resolution.
4 | UNHCR has closed all or has no implementation monitoring recommendations awaiting action, under this partnership?* | No | Note: UNHCR has 1 'Open' issue concerning procurement of laptops pending for some 2 months. This is limiting child protection case managers capacity to review pending cases.
TOPIC | PROTECTION AND SOLUTIONS
Q # | Question | Response by UNHCR | Response by Partner
5 | The partner has closed or has no protection and solutions challenges, including implementation monitoring recommendations awaiting action?* | Yes
6 | Additional protection challenges are identified (If ‘Yes’ - open "Implementation Monitoring" issue)?* | Yes | Note: Efforts are ongoing to resolve. CSI continues recruitment options to try and address the protection concern raised due to the absence of the female community worker surrounding GBV. Currently the male community worker continues their outreach while CSI looks to recruit a female staff member.
TOPIC | CONSTRUCTION AND INFRASTRUCTURE
Q # | Question | Response by UNHCR | Response by Partner
7 | The partner has closed all or has no construction and infrastructure challenges, including implementation monitoring recommendations awaiting action? | No. Attachments: Photo from UNHCR engineer of strip footings mid-construction. BoQ with the internal door specifications. Gantt Chart of construction workplan and most recent site meeting minutes outlining the milestones that are still pending but should have been completed 4 working days ago. | Note: Colleagues are following up to now close the 'Open' issue asap, within the due date, and we are just awaiting the quotation from the supplier for the alternative proposed internal door product. For the 'In dispute' issue, CSI kindly requests a meeting with the UNHCR engineer in order to find a resolution. Please see the site attendance list attached as proof that the necessary manpower has been present on site every working day since the start of implementation. There were severe storms for 2 days last week which impacted productivity on site. Attachments: PDF brochure (unpriced) of the proposed internal door product. Construction site attendance list to date for the project.
8 | The partner is applying a project management approach through the use of standardized construction templates? | Yes Attachments: Signed copies of all site meeting minutes and the CSI's progress reports to date for the project. | Note: CSI is providing fortnightly progress reports using a standardized template and, when the UNHCR engineer cannot be present for the bi-weekly site meetings, CSI provides the completed site meeting minutes using the template that UNHCR provided.
9 | Additional construction and infrastructure challenges are identified? (If ‘Yes’ - open "Implementation Monitoring" issue) | Yes Open an issue: record within the Issue that the UNHCR engineer observed that adequate site safety measures are not in place - some of the construction workers have not been wearing helmets and the site is not adequately demarcated. Upload photos for evidence inside the issue. | Note: CSI will ensure to address any new implementation monitoring issues raised.
TOPIC | OPERATIONAL CONTEXT
Q # | Question | Response by UNHCR | Response by Partner
10 | The partner has closed or has no operational challenges raised, including implementation monitoring recommendations awaiting action?* | Yes | Notes: The COVID-19 lock down disrupted a number of activities, but through the focused group discussions and local authorities support, some activities were able to continue.
11 | Additional operational challenges are identified? (If ‘Yes’ - open "Implementation Monitoring" issue)* | [The partner provides their update here via Note and/or attached narrative: surrounding any changes, variations or amendments from the original plan, and the circumstances or factors that prompted them? This might include changes resulting from individuals and/or community feedback, operational challenges or other constraints/opportunities encountered that required adapting the planned activities.] [The partner shares back their input via the Notes, at which point you may enter]: 'No.' | Notes: - BIA were conducted for UASC and children at risks, the cases received were children with disability (6 boys and 3 girls ), children in need of educational support (4 boys and 4 girls), children faced with inadequate basic needs (food, shelter and clothing) (3 boys and 8 girls), 2 Children in need of alternative care arrangement (1 boy and 1 girl ) and 01 case of teenage pregnancy. - BIA were conducted to inform intervention and home visits conducted with the respective households to ascertain the wellbeing and safety of the children. - One female Congolese child (female) at risk was reached through home visit in Makindye division. This was to provide a concrete discussion with the child and other family members. Also, to observe and capture details about the living conditions and follows up on reported case. - 02 BID panel meetings were held and 18 cases were discussed, this process is to aid provision of semi or permanent solutions to UASC and children at risks. - 02 unaccompanied minors were identified, BIAs conducted and placed in alternative care in addition to regular monitoring visits to ensure that the integrate in the families smoothly. - 31 children (14 boys and 17 girls) in need of specific needs children have been identified and assessed assistance is to be provided once the lockdown is lifted. - Provided counselling services to 23 (5 females) asylum seekers on the process of obtaining refugee status. - Conducted an assessment to identify which legal areas the community would require to know about. - Conducted one Legal Aid Clinic on Women’s day celebrations where 20 individuals (15 females) where counselled and provided with legal assistance. Provided legal assistance 15 cases (9 female) to individual cases that required physical protection. No additional operation challenges (other than COVID) were identified during this period.
TOPIC | RISK MITIGATION MEASURES
Q # | Question | Response by UNHCR | Response by Partner
12 | The Risk Register (document form) has treatments past due date or there are serious concerns about the successful implementation of treatments? (if yes - open " implementation monitoring" issue and explain the risk and treatments to be actioned)* | Yes Open an issue: for CSI to review and revise/update their Risk Register. Project control may wish to share via the 'Formal Partner Review' workflow, for a joint review, informing Programme of any updates.
13 | The Risk Register (document form) requires revision? (if yes –initiate a workflow to revise and resubmit the Risk Register)* | Yes | Note: Risk Register is under review and will be updated accordingly.
TOPIC | PROCUREMENT
Q # | Question | Response by UNHCR | Response by Partner
14 | Additional procurement challenges are identified? (If ‘Yes’ - open "Implementation Monitoring" issue to follow up) | No
15 | Partner has closed all or has no procurement challenges, including implementation monitoring recommendations awaiting action? | No | Note: CSI has one open pending issue related to procurement, which CSI is working on with UNHCR supply in order to close shortly.
TOPIC | STRENGTHENED PSEA MEASURES
Q # | Question | Response by UNHCR | Response by Partner
16 | The partner has undertaken progress towards their PSEA Capacity Strengthening Implementation Plan? (N/A if partners have full PSEA capacity)* | Drop-down menu choice: - Partially | Note: CSI has completed some of the CSIP activities as scheduled in the UNPP, and has accordingly improved from low to medium capacity. It is expected that at the end of the CSIP duration, CSI would have completed the remaining two activities and will become with full capacity.
TOPIC | Notes ON IMPLEMENTATION PROCESS
Q # | Question | Response by UNHCR | Response by Partner
17 | Implementation is proceeding as planned towards indicator targets? Attach evidence of partner’s reported actuals against planned output indicators (If ‘No’ - open "Implementation Monitoring" issue)* | Drop-down menu choice: - Yes Attachments: a copy of the validated indicator dataset (e.g. an extract from ActivityInfo or an Excel table) is uploaded here as supporting evidence. | Note: the reported actuals are from one month earlier. However a variation and change in targets have been discussed with UNHCR and agreed according to reprioritization. See attached meeting minutes with UNHCR Sub-Office.
18 | Record the most recently recorded progress towards each planned indicator - as a percentage (each indicator progress % = each indicator total target divided by latest reported actual, where relevant)* | 1. # of government officials trained on status determination: 25% 2. Number of people supported to obtain civil status, identity or legal status documentation: 10% 3. Number of people registered on an individual basis: 21% 4. # advocacy, interventions conducted: 22% 5. Number of people supported to obtain civil status, identity or legal status documentation: 25% 6. Number of people who benefitted from specialized GBV programmes: 120% | Note: 1) Proceeding with the activities and achieving the targets is going as planned for this time of the year. 2) For the output indicator named "XXX" there is a high level of progress 120%. The reason is that there were more cases reported on GBV incidents higher than planned, due to the influx that occurred at the beginning of the year, the awareness raising activities, and to the availability of complaint boxes in all services/distribution locations. This needs to be discussed incase an amendment of the agreement is needed. While the output indicator named "YYY" is very low at 10% at this time of the year, due to some delays from the government side in facilitating the process. A discussion is taking place with the government to expedite the process.
19 | Any Other Observations/Remarks | Based on the latest reporting, CSI is progressing well towards the planned indicators.
TOPIC | PREPARED AND SIGNED BY UNHCR
Q # | Question | Answer
20 | Name, Title* | xxxxxxxxxxxxx
21 | Signature*
TOPIC | PREPARED AND SIGNED BY PARTNER: OTHER (IF AVAILABLE)
Q # | Question | Answer
22 | Partner Acceptance Status | Drop-down menu choice: - Accepted
23 | Partner Notes | None
24 | Name, Title | xxxxxxxxxxxx
25 | Signature