## Guidance
PROJECT FINANCIAL VERIFICATION REPORT- PMC03
Guidance on how to answer each question in the long form |  |  | Note: Questions with * are mandatory.
UNHCR Project Control finds the correct Field Inspections PMC03 form. UNHCR Project Control will "Start" & complete questions 1-51 within the PMC03 form, attaching supporting documentation to a particular question and/or raising an implementation monitoring Field "Issue" (assigning the Issue to the partner) where necessary, and signing when complete. UNHCR Project Control then assigns the PMC03 to the most senior Project Control focal point in the operation (UNHCR approver), entering a Due Date for their review and signature. Once the UNHCR approver has answered questions 52 and 53, approving the PMC03 internally, the UNHCR approver reassigns the PMC03 to the Partner Organization, entering a Due Date for their review and signature. The Partner Administrator receives the PMC03 (via an email summary) and can assign it to a colleague. The partner can add notes and/or any supporting evidence to any of the questions and/or completes questions 54-57, before assigning the PMC03 back to UNHCR. UNHCR Project Control can edit the PMC03 based on the Partner's notes and supporting evidence, and assign it back to the Partner (as required) after the UNHCR approver has provided their internal approval. Once the PMC03 is completed in full, UNHCR Project Control 'closes' the status of the PMC03. The most senior Project Control focal point in the operation will download the closed PMC03 as a PDF and upload it to the PFR workflow as a supplementary file for the 2nd stage approval step. In case any changes are required, UNHCR can reopen the PMC03 for editing at any time.
TOPIC | PRELIMINARY INFORMATION
Q # | Question | Type of Answer | Guidance
1 | Implementer* | Free text | Write out the full name of the partner as it appears under the "implementer" column in the Aconex Document Register. You can also copy and paste the exact name of the partner from the Document Register. However, since this PMC03 will be attached to the PFR workflow in Aconex, you will be able to easily find the documentation via the PFR associated with the implementer.
2 | Partner Agreement / Contract* | Free text | Enter the Cloud ERP Contract ID # for the partnership agreement. i.e. Cost Centre + Y + last two digits of year + M (for migrated partner record) or P (new partner record) + Partner Supplier Number (last six digits). You can copy and paste the exact code from the "Partner Agreement / Contract" column in the Aconex Document Register. However, since this PMC03 will be attached to the PFR workflow in Aconex, you will be able to easily find the documentation via the PFR associated with the implementer.
3 | Type of Verification?* | Drop-down menu choice: - On-site - Remote - Combined | Select the applicable drop-down option for how the financial verification is being conducted: - On-site = at the partner's office/location where financial information/reports are generated and stored. - Remote = not at the partner's office/location where financial information/reports are generated and stored. - Combined = a combination of on-site and remote.
4 | If remote only, please justify | Free text | Explain the reason for deciding to conduct a remote verification. UNHCR only uses remote financial verification in exceptional circumstances for partners with low-risk rating in ICA/Q, and/or in cases where recent PMC03 verifications have not reported weaknesses. Other considerations could include security and partner access issues, volume of activities/size of budgets, if there are recent concerns for possible mismanagement.
5 | Location of the Financial Verification* | Free text | Name of the location where the financial verification is being conducted and type of office type
6 | UNHCR Staff Members Conducting the Financial Verification* | Free text | Write out the full name (first name and family name) and job title for all UNHCR personnel conducting the financial verification. It is possible that there is only one UNHCR colleague conducting the financial verification.
7 | Partner Focal Persons Involved in the Financial Verification* | Free text | Write out the full name (first name and family name), job title, email address and phone number for all partner personnel involved in the financial verification. It is possible that there is only one person from the partner organization involved in the financial verification.
TOPIC | PURPOSE OF THE FINANCIAL VERIFICATION - COMPLETE ALL THAT APPLY AND SELECT “IMPLEMENTATION MONITORING” AS AN ISSUE TYPE IF YOU NEED TO OPEN AN ISSUE:
Q # | Question | Type of Answer | Guidance
8 | To verify compliance with the Partnership Framework Agreement and Project Workplan, including Governing Clauses and approved Financial Plan or other applicable requirements. | Yes / No | Select 'Yes' if part (or all) of the purpose of this financial verification is to verify if the partner is complying with the articles of the Partnership Terms of the Partnership Framework Agreement, the contents of the project workplan contract terms, and the approved financial plan, as well as other contractual requirements as applicable. Select 'No' if it is not required to verify this compliance with this project financial verification.
9 | To evaluate whether internal controls are in place and functioning, including payment and bank management, procurement, management of subcontracted partners, personnel engagement & payments, budget & asset management, & general control environment. | Yes / No | Select 'Yes' if part (or all) of the purpose of this financial verification is to evaluate whether internal controls are in place and functioning, including payment and bank management, procurement, management of subcontracted partners, personnel engagement & payments, budget & asset management, & general control environment. Select 'No' if it is not required to evaluate internal controls with this project financial verification.
10 | To evaluate whether the financial expenditure of the project is proceeding in accordance with the last reported actuals/results (outputs). | Yes / No | Select 'Yes' if part (or all) of the purpose of this financial verification is to evaluate whether the financial expenditure of the project is proceeding in accordance with the last reported actuals/results. Select 'No' if it is not required to evaluate the financial expenditure in accordance with reported results with this project financial verification.
11 | To evaluate the PFR in order to ascertain that it fairly represents the financial situation of the project and that UNHCR funds have been used for the intended purpose. | Yes / No | Select 'Yes' if part (or all) of the purpose of this financial verification is to evaluate the PFR in order to ascertain that it fairly represents the financial situation of the project and that UNHCR funds have been used for the intended purpose. Select 'No' if it is not required to evaluate the PFR with this project financial verification.
12 | To ensure project expenses are incurred according to agreed Financial Plan, charged to appropriate account codes and budget lines, within allowed limits for intra budget lines transfers. | Yes / No | Select 'Yes' if part (or all) of the purpose of this financial verification is to ensure project expenses are incurred according to the agreed Financial Plan, charged to appropriate account codes and budget lines, within allowed limits for intra budget lines transfers. Select 'No' if it is not required to ensure project expenses are incurred according to the agreed Financial Plan with this project financial verification.
13 | To follow up on any UNHCR-supported project management capacity development activities. | Yes / No | Select 'Yes' if part (or all) of the purpose of this financial verification is to follow up on any UNHCR-supported project management capacity development activities. Select 'No' if it is not required to follow up on any UNHCR-supported project management capacity development with this project financial verification.
14 | Other reasons (please specify) | Free text | If there are other reasons as to why this financial verification is being conduction, which are not covered in questions 8 - 13, provide a clear explanation of the reasons and why they are valid for this project.
15 | Was the Project Performance Verification completed?* | Drop-down menu choice: - Yes - No, extract and attach "Implementation Monitoring" issues report | Select the applicable drop-down option as to whether the project performance verification has been recently completed to inform this financial verification - either 'Yes' or 'No'. If 'no', download the report of implementation monitoring issues for this project that are awaiting action (i.e. “ready to inspect”, “open” and “in dispute”) and attach it to this question.
SCOPE AND FINDINGS: FOR EACH OF THE FOLLOWING, RECOMMENDATIONS MUST BE RAISED WITH AN “IMPLEMENTATION MONITORING” ISSUE. IF ANSWERED ‘YES,’ PLEASE ATTACH RELEVANT SUPPORTING DOCUMENTATION.
TOPIC | ELIGIBILITY OF EXPENSES CLAIMED FOR ACTIVITIES, (PLEASE ATTACH SUPPORTING DOCUMENTS FOR THE TRANSACTIONS/VOUCHERS VERIFIED)
Q # | Question | Type of Answer | Guidance
16 | Expenses charged to appropriate account codes and outputs, within allowed budget flexibility. (If ‘No’ - open an ‘Issue’)* | Yes / No | Firstly, ask the partner to explain how it determines expenses to be charged to UNHCR. While most partners use their general ledger for this purpose, the partner may have devised an alternative approach for tracking expenses for UNHCR projects. Then, select the expenditure lines where the verification will focus. Emphasis is given to material expenditure (i.e. large expenditure lines, goods and property purchases and related documents, staff loans, salary, communication costs, rental, fuel, vehicle usage, etc.). By conducting an inspection of records, assess whether expenses have been charged to appropriate account codes and outputs, within the allowed budget flexibility (between 30 - 50% between different outputs) that is stipulated in the contract terms of the project workplan. There is 100% budget flexibility within one output (in compliance with the budget flexibility conditions stipulated in the project workplan). There are 3 types of inspections of records: 1. One hundred per cent examination: Review all expenses claimed on an expenditure line item, and examine all contracts, where there is a small number. 2. Zero per cent examination: This occurs when UNHCR project control determines that a type of expense claimed does not have to be tested. 3. Sampling of transactions: This aims to verify whether expenses claimed are eligible and involves testing less than 100 per cent of the items claimed in a PFR. There is an inherent risk to sampling, as sample results may not be representative of the entire expenditure. Professional judgment is used to determine the size of the sample. Generally, a smaller sample is reliable when the partner’s internal control environment is strong while for high risk partners with weak internal controls, the sample size is also bigger. As part of the inspection, check the expenses recorded on each selected line by: 1. Comparing the amount claimed with the balance of the relevant general ledger account (or tracking system used by the partner for determining expenses to be charged to UNHCR projects). 2. Selecting transactions to test for proper supporting documentation. Generally, transaction testing entails checking the relevant payment voucher for: i) Completion. ii) Correct recording of expenditure in the relevant expenditure line. iii) All supporting documents. iv) Authorization and certification. v) Compliance with policy and procedure. vi) A recalculation of the payroll and trace approvals of the salary authorization document. This may involve examining employee time sheets and noting the signature and supervisory approval. vii) Determination of whether the project costs are correct as per the expenditure reported and the period. viii) Determination of whether the costs are allowable and in compliance with the provision of the project workplan (NB: this is applicable to the inspection for question 17 below). Select 'Yes' if expenses have been charged appropriately and the contractual budget flexibility has been adhered to. Select 'No' if any expenses have not been charged appropriately and/or if the budget flexibility limit has been exceeded. Raise an implementation monitoring issue with the category "eligibility of expenses claimed" and provide a recommendation for the partner to correct their expenses in adherence with the contract terms. Assign the issue to the partner for their follow up. Attach the sample of tested transactions to the question and any other supporting documents (as applicable).
17 | Expenditures are in compliance with the project purpose, for direct project costs and/or agreed direct shared costs, while indirect costs remain part of the Indirect Support Costs. (If ‘No’ - open an ‘Issue’)* | Yes / No | By conducting an inspection of records (see guidance for Q16 for more details), assess whether expenditures charged to the project are in compliance with the project purpose and fall within their correct cost category. Direct programme costs are 100% directly related to one output. Direct shared costs are costs that a partner apportions across more than one output under the financial plan of one project workplan. These are also used by the partner when representing a shared cost involving another donor. For instance, if UNHCR does not cover 100 per cent of the overall cost of an item or service, the partner may share this cost with funds provided by another donor. Indirect support costs are the costs needed to manage and run an organization. They support the delivery of activities but are not directly related to implementation and can include policies, frameworks, systems, overhead and capacity-strengthening costs that enable a project or organization to operate successfully. It is not practical to charge indirect costs to individual funding arrangements under direct costs, but without these costs present, projects and programmes cannot be delivered effectively, efficiently and safely. Some red flags to take into account: (a) Expenditures not aligned with project objectives or activities, (b) Misallocation of expenses, such as charging personnel costs to non-project-related costs, (c) Inaccurate categorization of indirect support costs as direct programme expenses, (d) Lack of documentation or justification for project expenditures, (e) Excessive or unauthorized spending beyond the approved budget. Select 'Yes' if expenditures are in compliance with the project purpose and fall within their correct cost category. Select 'No' if any expenditures are not in compliance with the project purpose and/or if any expenditures are not charged to the correct cost category. Raise an implementation monitoring issue with the category "eligibility of expenses claimed" and provide a recommendation for the partner to correct their expenses in adherence with the contract terms. Assign the issue to the partner for their follow up. Attach the sample of tested transactions to the question and any other supporting documents (as applicable).
TOPIC | FUNDS/CASH MANAGEMENT
Q # | Question | Type of Answer | Guidance
18 | Bank statements: related to the project reconcile with balances on the partner cash book (if yes - attach bank statements & general ledger/ transaction list to this question / if no - open an "issue")* | Drop-down menu choice: - Yes - No - Already submitted | Partners are required to nominate one bank account to which UNHCR will transfer prepayments for the project. They can use a pooled bank account without prior approval from UNHCR if they have adequate mechanisms in place to trace the use of UNHCR funds and they allow UNHCR and its auditors to conduct financial verifications. Assess whether bank statements related to the project reconcile with balances on the partner's cash book by applying the required adjustments for outstanding checks issued by the partner and uncleared deposits. This process should consider verifying if the name of the bank account holder is the same as the legitimate name of the partner as stipulated in the UNHCR official supplier records. It is important to check if bank interest earned is credited or apportioned by the size of UNHCR funds and the other funds in the pooled accounts (if applicable). Select the applicable drop-down option as to whether bank statements are reconciled with balances: - If yes, attach the bank statements (for all bank accounts used for project related transations) and general ledger assessed to this question. - If no, raise an implementation monitoring issue with the category "funds/cash management" and provide a recommendation for the partner to make the necessary corrections. Assign the issue to the partner for their follow-up. - Already submitted = bank statements have already been submitted and assessed by UNHCR and there is no need to re-assess the reconciliations.
19 | Bank reconciliations: are performed on a monthly basis (if yes - attach bank reconciliations / if no - open an "issue")* | Drop-down menu choice: - Yes - No - Already submitted | Review the bank reconciliations related to the project. The accounts payable should be reconciled with the general ledger at least on a monthly basis. Select the applicable drop-down option as to whether bank reconciliations are performed on a monthly basis: - If yes, attach the bank reconciliations. - If no, raise an implementation monitoring issue with the category "funds/cash management" and provide a recommendation for the partner to increase their frequency of bank reconciliations or to address any other discrepencies noted. Assign the issue to the partner for their follow up. - Already submitted = bank statements have already been submitted and assessed by UNHCR and there is no need to re-assess the bank reconciliation process.
20 | Bank reconciliations: procedures to follow up on outstanding cheques are in place (if no - open an "issue")* | Drop-down menu choice: - Yes - No - Not applicable | When cheques are used, this question requires checking if they are tracked through the numbering of cheques and the archiving of cheque slips. The list of cheque signatories should be reviewed regularly by the partner to make sure that only current employees are authorized signatories. Cheque payments are approved by at least two authorized persons to ensure a segregation of duties, an authorized cheque signatory and a member of the finance/admin team. Cheque payments are supported by appropriate documentation justifying the disbursement. Cheque reconciliations are approved by a supervisor and there is segregation of duties between the preparer and approver of the reconciliation. Undisbursed funds should be appropriately refunded to UNHCR. Inquire with the partner about their procedures to follow up on outstanding cheques and review the evidence they provide for having such procedures in place. Select the applicable drop-down option as to whether there are procedures to follow up on outstanding cheques in place or not: - If yes, attach any supporting evidence as applicable (not mandatory). - If no, raise an implementation monitoring issue with the category "funds/cash management" and provide a recommendation for the partner to develop procedures for following up on outstanding cheques. Assign the issue to the partner for their follow up. - If not applicable, the partner does not use cheques and this question therefore does not apply.
21 | Cash management procedures: segregation of duties, cash recipients’ identification, PDM, required documentation, physical cash safeguard measures, surprise cash counts are documented. (If ’No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Verify if, when it comes to cash management, the partner applies a segregation of duties, records the identification of cash recipients, conducts post-distribution monitoring, uses physical cash safeguard measures and documents surprise cash counts. The partner may record cash in and cash out movements in a petty cash journal. For cash-based assistance (inclusive of all modalities - mobile money, vouches, bank transfers etc.) given to forcibly displaced and stateless persons, a detailed list of beneficiaries should be maintained by the partner. This list should be signed off by the individuals distributing the cash, an authorized supervisor and the recipients of the cash. Select the applicable drop-down option as to whether the partner has adequate cash management procedures in place. If the partner is missing any of the aforementioned elements, select 'No' and raise an implementation monitoring issue. Use the Issue the category of "funds/cash management" and provide a recommendation for the partner to enhance their cash management procedures. Assign the issue to the partner for their follow up. Attach any supporting evidence of the cash mangement procedures that the partner uses (not mandatory).
22 | Reported expenditures: in the currency set out in the Financial Plan or partner applied exchange rates aligned to partnership agreement clauses. (If ’No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Verify that the reported expenditures in the PFR are using the same currency as set out in the final agreed financial plan. If a partner spends in another currency or currencies, this must be converted to the reporting currency. Expenses from a dedicated bank account are converted using the bank's exchange rate on the withdrawal/payment date, while expenses from a pooled bank account follow the partner's internal rules for expense recognition and the partner documents the applied exchange rates. This ensures consistent reporting across different currencies and bank accounts. Select the applicable drop-down option as to whether the partner has reported expenditures in the currency set out in the financial plan or has applied the correct exchange rate to convert the expenses from the different currency(ies). If 'No', the partner has not reported expenditures in the financial plan currency and/or has not converted the expenditures using the correct exchange rate, raise an implementation monitoring issue with the category "funds/cash management" and provide a recommendation for the partner to correct the currency of the expenditures. Assign the issue to the partner for their follow up. Attach any supporting evidence for the currency (and/or currency conversion) of the reported expenditures (not mandatory).
23 | Has any interest income and miscellaneous revenue earned during the project implementation been properly recorded? (If ’No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Verify if the partner has properly recorded any interest income and miscellaneous revenue earned during the project implementation. Any interest gained by a partner directly due to a UNHCR-funded agreement must be used by the partner for activities that are consistent with the goals of the partnership and will be documented in accordance with the partner’s financial rules. However, if the partner’s financial regulations necessitate the return of the interest income, it will be repaid to UNHCR and reported when submitting the PFR. Non-interest revenue received by the partner directly due to a UNHCR-funded agreement is reported by the partner with the next PFR after the revenue is received. This includes insurance revenue resulting from project-related insurance claims, income generating activities and value-added tax (VAT). The representative or director has the authority to approve if such non-interest revenue will be used by the partner for activities that are consistent with the goals of the partnership, or if the amount will be refunded to UNHCR. All such decisions are documented for audit purposes in the operation’s SharePoint. Select the applicable drop-down option: - Yes = Partner has properly recorded any interest income and/or miscellaneous revenue earned during the project implementation Or, this question is not applicable because the partner has not earned any interest income or miscelleaneous revenue during project implementation. - No = Partner has NOT properly recorded any interest income and/or miscellaneous revenue earned during the project implementation. If the partner has not properly recorded the interest income/miscellaneous revenue, raise an implementation monitoring issue with the category "funds/cash management" and provide a recommendation for the partner to properly record this interest income/miscellaneous revenue. Assign the issue to the partner for their follow up. Select 'No' if this question is not applicable and add a note to the answer to explain that it is not applicable. The partner will not be able to add a note in response to this question but their feedback is not required since it is not applicable. Attach any supporting evidence to the question (not mandatory).
TOPIC | PROCUREMENT
Q # | Question | Type of Answer | Guidance
24 | The partner complies with their own applicable procurement policies. (If ’No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Conduct an analytical review of how the partner adheres to their own applicable procurement policies/procedures. Take a sample of procurements completed (number in the sample depends on the scale of procurement within the partnership agreement) for the project to date and analyse if the actions taken were in compliance with the partner's procurement policies/procedures. Procurement must be conducted in an ethical manner, with total impartiality and without any preferential treatment. Partners should have a zero-tolerance policy on fraud and corruption. Partners should not condone corrupt and fraudulent practices or any other form of misconduct including conflict of interest. Partners should ensure that they have systems in place to prevent and detect fraud, discipline and report unethical behavior and corrupt practices in order to foster a culture of integrity and accountability. Partners should commit to maintain the highest standards and to immediately identify, address, mitigate, and report all instances in which these are compromised. Partners should demonstrate Code of Conduct for employees addressing ethical principles mentioned above. Select the applicable drop-down option: - Yes = Partner complies with their own applicable procurement policies. - No = Partner does not comply with their own applicable procurement policies or this question is not applicable because the partner has not conducted any procurement. If the partner is lacking compliance, raise an implementation monitoring issue with the category "procurement" and provide a recommendation for the partner to improve their compliance to their own procurement policies. Assign the issue to the partner for their follow up. If not applicable, add a note to the answer to explain that it is not applicable. The partner will not be able to add a note in response to this question but their feedback is not required since it is not applicable. Attach any supporting evidence to the question (not mandatory).
25 | Does the partner have strong procurement processes in place, such as sourcing procedures, segregation of duties, no conflict of interests, expertise and timely delivery of expected quality/quantity? (If ’No’ - open an ‘Issue’)* | Yes / No | Conduct an analytical review of the partner's procurement processes by sampling a number of procurements completed (number in the sample depends on the scale of procurement within the partnership agreement) for the project to date. Read over the partner's procurement policies/procedures to be familiar with the requirements. From the review of this sample, verify if the partner followed the required procedures on bid solicitation, handling and receipt of bids, technical and financial evaluations, contract and vendor management, had a clear segregation of duties, had no conflicts of interest (or dealt with them according to their procurement policies) and if the items procured where delivered on time in the expected quality and quantity. When applicable, ask for an independent verification supporting the partner’s sourcing procedure by contacting the selected supplier to confirm the procurement activities. The Partner’s regulations should reflect the principle of segregation of duties between requisitioning and procurement entities by specifying their separate and distinct functions within the overall procurement process and finally between the teams that executes the payment. Are supporting documents stamped as "Paid" and marked with the donor or project name after payment has been made? Or, does the accounting system otherwise have inbuilt controls to ensure payments cannot be made more than once or claimed/charged against more than one funding source? Select 'Yes' if the partner has strong procurement processes in place which cover, but are not limited to, sourcing, segregation of duties, conflict of interest, expertise in procurement, handling and receipt of bids, technical and financial evaluations, good and services delively/receipts, contract and vendor management. Select 'No' if the partner's procurement processes lack any of the key procurement elements including but not limited to; adequate sourcing procedures, segregation of duties, conflict of interest, expertise in procurement, handling and receipt of bids, technical and financial evaluations, good and services delively/receipts, contract and vendor management , segregation of duties, conflict of interest management, Raise an implementation monitoring issue with the category "procurement" and provide a recommendation for the partner to improve their procurement processes. Assign the issue to the partner for their follow up. Or, select 'No' if this question is not applicable because the partner has not conducted any procurement. Add a note to the answer to explain that it is not applicable. The partner will not be able to add a note in response to this question but their feedback is not required since it is not applicable. Attach any supporting evidence to the question (not mandatory).
26 | While reviewing supporting documents: where confirmation had to be sought directly from suppliers for information on the invoices (prices, quantity delivered, name/contact details of suppliers), there were confirmed findings? (If ’Yes’ - open an ‘Issue’)* | Yes / No | By sampling a number of invoices from supplier(s) and reviewing the associated correspondence/documentation between the partner and the supplier(s) in question, verify whether the partner received confirmation on the invoice information sought - i.e. prices, quantity delivered, name/contact details of supplier(s) etc. Ask for an independent verification supporting the partner’s correspondence/documentation by contacting the selected supplier(s) to confirm they were responsible for providing the requested information. Attach the WP's with the sample selection and test documentation. This process will also include checking that the invoices are approved according to the delegation of authority within the partner's organization. Select 'Yes' if there were confirmed findings for the requested information from the supplier(s) on the invoices. Select 'No' if there were no confirmed findings for the requested information from the supplier(s) on the invoices. Raise an implementation monitoring issue with the category "procurement" and provide a recommendation for the partner to improve their communications with suppliers. Assign the issue to the partner for their follow up. Or, select 'No' if this question is not applicable because the partner has not conducted any procurement. Add a note to the answer to explain that it is not applicable. The partner will not be able to add a note in response to this question but their feedback is not required since it is not applicable. Attach copies of the samples of the invoices reviewed to the question (not mandatory). This should be a requirement.
TOPIC | HUMAN RESOURCES AND PAYROLL EXPENSES
Q # | Question | Type of Answer | Guidance
27 | The Partner complies with their policy/guidance on human resources management. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Conduct an analytical review of how the partner adheres to their own applicable human resources (HR) management policy/guidance by sampling a number of HR management tasks completed (number in the sample depends on the size of the HR management team for the project) for the project to date. Read over the partner's policiy/guidance on HR management to be familiar with the requirements. From the review of this sample, verify if the partner complies with their own recruitment, employment and/or personnel policy/guidance. Select the applicable drop-down option: - Yes = Partner complies with their policy/guidance on human resources management. - No = Partner does not comply with their policy/guidance on human resources management and raise an implementation monitoring issue with the category "human resources and payroll" and provide a recommendation for the partner to improve their compliance with their HR management policy/guidance. Assign the issue to the partner for their follow up. Attach any supporting evidence to the question (not mandatory).
28 | There is a system for tracking time and attendance of staff (full time and part time) for the time spent on the project and linked to salaries charged to the project. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Assess the system in place for tracking time and attendance of staff to ensure that staff charged to the project were, indeed, contributing to the project. Where only part of a staff member's costs are charged to a project, assess whether the partner has a system in place that ensures the amount charged to the projet corresponds with the actual hours spent by the staff member on project objectives as per attendance and timesheets or other supporting documents. Review the partner's documented procedures on staffing and assess integration with payroll systems to validate the existence of a time and attendance tracking system for project staff. Look for inconsistencies between reported hours worked and salaries charged to the project, as well as potential for inflating of work hours and where staff may claim payment for the same hours from multiple projects. Pay attention to possibilities of double dipping, if the same reported work hours are claimed by the partners from the same donors, which could indicate errors or fraudulent activities and require to be reported to IGO in case there are indication for misconduct/fraud. Select the applicable drop-down option: - Yes = Partner has a system for tracking time and attendance of staff for the time spent on the project and linked to salaries charged to the project. - No = Partner does not have a system for tracking time and attendance of staff for the time spent on the project and linked to salaries charged to the project or there are other issues that lead to doubts on personnel costs charged to into the PFR. Raise an implementation monitoring issue with the category "human resources and payroll" and provide a recommendation for the partner to develop a tracking system. Assign the issue to the partner for their follow up. Attach any supporting evidence to the question (not mandatory).
29 | General ledger payroll versus PFR: confirm amount charged to a project for selected staff does not exceed what the Partner is contractually/legally obliged to pay. Supporting documents for salary calculation is in place. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Conduct a random comparison between the general ledget amount of payments to staff and the amount charged to UNHCR to verify if the amount charged to the project in respect of staff does not exceed the amount that the partner is contractually/legally obliged to pay to staff for the period of time covered by the signed project workplan (implementation period). Additionally, ensure that supporting documents for salary calculations, like timesheets or employment contracts, are readily available. This may include checking if the review of payroll is performed before processing the payment, including an analysis of variances vs prior period of overtime, bonuses and vacation and personnel expenses (including travel etc.) are approved independently to verify that they are valid and in compliance with the project agreement. The partner’s personnel are remunerated in accordance with the partner’s human resources policies, systems and procedures. UNHCR does not require partner personnel lists to be annexed to project workplans, nor does it have a global standardized contribution cap or limit for partner personnel costs. The partner does not charge more staff costs to a UNHCR-funded project than the amount defined in the human resources policies and employment contract. If a partner reports to UNHCR that it has made excessive payments to a staff member from UNHCR project funds, the excess amount is classified as an ineligible expense. Additionally, the partner is prohibited from coercing employees into providing any portion of their net salary and reporting it to UNHCR as an expenditure within personnel costs. Finally, all expenses claimed in the PFRs are those fully funded by UNHCR and cannot be reclaimed again to another donor for double funding. Such actions constitute attempted fraud and a breach of the agreement and may give rise to termination due to misconduct. Select the applicable drop-down option: - Yes = The amount charged to the project for selected staff does not exceed what the partner is contractually/legally obliged to pay and there are supporting documents for salary calculations in place. - No = The amount charged to the project for selected staff exceeds what the partner is contractually/legally obliged to pay and/or there are not any supporting documents for salary calculations in place. Raise an implementation monitoring issue with the category "human resources and payroll" and provide a recommendation for the partner to lower the staff charges to the project and/or document salary calculations. Assign the issue to the partner for their follow up. Attach any supporting evidence, such as copies of supporting documents for salary calculations in place, to the question (not mandatory).
30 | Assess staff existence & salary received: select sample staff members & verify employment records; review benefits (net pay) received versus reported (salary slips) & enquire if any pay back was requested by the Partner. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Assess the existence of staff for whom the costs are charged to the project by selecting a sample of current staff members and former staff members who worked on the project and verify the employment records, as well as ensuring that the amounts of benefits confirmed as received correspond to the amounts reported in the PFR. Ask for an independent verification supporting the partner’s salary/benefits reported by contacting the staff members directly to confirm their involvement in the project implementation and salaries received. Enquire about any payback requests by partner to staff members, inquire if staff member works for projects of other donors and assess if the time charged to the UNHCR project is reasonable vs to the time spent to other donor's project or if reported as 100% for the time sheet which could signal double dipping, assess the risks for staff inflating their work hours and claim payment for the same work across multiple projects. Also, look out for discrepancies in reported salaries or duplicate submissions of timesheets or expenses. Document the detailed examination and findings. Select the applicable drop-down option: - Yes = The staff salaries charged to the project align with the number of staff who actually have worked and/or continue to work on the project, and the benefits received correspond to the amounts reported in the PFR. - No = There are discrepancies between the number of staff salaries charged to the project and the number of staff who have worked and/or continue to work on the project, and/or the benefits received do not correspond to the amounts reported in the PFR. Raise an implementation monitoring issue with the category "human resources and payroll" and provide a recommendation for the partner to address these staff salary/benefit discrepancies. Assign the issue to the partner for their follow up. Attach any supporting evidence to the question (not mandatory).
TOPIC | FINANCIAL AND PROJECT RECORDS
Q # | Question | Type of Answer | Guidance
31 | Confirm whether financial and project records are properly maintained and well organized, and that the accounting system complies with the requirements of the Project Workplan. (‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Verify whether the partner's financial and project records are properly maintained and well-organized, and whether the accounting system complies with the requirements of the project workplan. Questions to consider are as follows: Does the partner maintain all its financial and project records in a way that enables the ready identification of relevant documentation? Does the partner create and manage records consistently, where it is possible to distinguish between valuable and obsolte records and evidence? Does the partner store records safely and dispose of records appropriately? Does the partner use an accounting system that records sufficient details of each transaction to allow it to be linked to the corresponding documentation and allocated to the relevant funding source? Does the accounting system have inbuilt controls to ensure payments cannot be made more than once or claimed against more than one funding source? Is access to the accounting system protected through the use of usernames and passwords? Do different users have different access rights so that they are only able to review or make changes to information that is relevant to their function? Is the accounting system backed up to a secure offsite location on a sufficiently regular basis? Select the applicable drop-down option: - Yes = The partner's financial and project records are properly maintained and well-organized, and the accounting system complies with the requirements of the project workplan. - No = The partner's financial and project records are not properly maintained and are not well-organized, and/or the accounting system does not comply with the requirements of the project workplan. Raise an implementation monitoring issue with the category "financial and project records" and provide a recommendation to improve their maintenance of financial and project records and/or update their accounting system to comply with the project workplan. Assign the issue to the partner for their follow up. Attach any supporting evidence to the question (not mandatory).
32 | Does the Partner rely on paper/Excel based accounting system? (‘No’ - open an ‘Issue’). Recommendation for acquisition of affordable software could be suggested, if applicable.* | Drop-down menu choice: - Yes - No | Ask the partner if they rely on a paper/excel based accounting system and request to see the accounting system they use, as well as observe the partner staff carrying out accounting tasks with their system. Relying on a paper or Excel-based accounting system may present some red flags, including limited accuracy, efficiency, transparency, increased risk of errors, and limited scalability. Without additional and proper controls to support it, such as robust validation mechanisms or audit trails, there's a heightened risk of financial inaccuracies, inefficiencies, and operational challenges. Consequently, transitioning to a more reliable accounting software solution is recommended to enhance financial management capabilities, mitigate risks associated with manual systems. Select the applicable drop-down option: - Yes = The partner relies on a paper or excel based accounting system. Raise an implementation monitoring issue with the category "financial and project records" and provide a recommendation for the partner to consider using an affordable software system for their accounting. Assign the issue to the partner for their follow up. - No = The partner does not rely on a paper or excel based accounting system. Attach any supporting evidence to the question (not mandatory). NB: The question contains an error - you do NOT need to raise an 'Issue' if the answer is no. You should raise an 'Issue' if the answer is yes.
TOPIC | ASSET MANAGEMENT - WITHIN THE MFT OR RELEVANT UNIT I.E. SUPPLY AS APPLICABLE
Q # | Question | Type of Answer | Guidance
33 | Partner has procedures in place to store, record and safeguard assets under its responsibility, whether purchased from funds provided by UNHCR or provided under a “Right of Use Agreement”. (‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Ascertain if the partner has procedures in place to store, record and safeguard assets under its responsibility, whether purchased from funds provided by UNHCR or provided under right of use conditions. Keep in mind that the programme function coordinates a physical verification exercise of all assets under the ownership and control of UNHCR (i.e., those that appear on UNHCR’s asset list in Cloud ERP), loaned to partners, through the right of use, on an annual basis. Partners are required to facilitate the visit of assets and to cooperate with UNHCR or other duly authorized persons. However, goods and property bought and controlled by a partner under a project workplan are recognized as a partner expense when the partner acquires the relevant goods. Therefore, goods and property bought by a partner with UNHCR funds are not required to be reported on or verified by UNHCR. Similarly, assets previously controlled and owned by UNHCR that are transferred to the partner are also not required to be reported on, nor verified. Questions to consider: Does the partner maintain a comprehensive and up-to-date fixed asset register, that records all relevant details (such as purchase date, cost, condition, location, tag number, serial number, and owner) for each asset held? Are there sufficient measures and procedures in place to protect assets from theft, damage or misuse? Select the applicable drop-down option: - Yes = The partner has procedures in place to store, record and safeguard assets under its responsibility, whether purchased from funds provided by UNHCR or provided under right of use conditions. - No = The partner does not have procedures in place to store, record and safeguard assets under its responsibility, whether purchased from funds provided by UNHCR or provided under right of use conditions. Raise an implementation monitoring issue with the category "asset management" and provide a recommendation develop procedures for the storage, recording and safeguarding of assets under its responsibility. Assign the issue to the partner for their follow up. Or, select 'No' if this question is not applicable and add a note to the answer to explain that it is not applicable. The partner will not be able to add a note in response to this question but their feedback is not required since it is not applicable. Attach any supporting evidence to the question, for example a copy of the partner's asset register (not mandatory). NB: The question contains an error - there is no standalone "Right of Use Agreement" anymore and there are right of use conditions written into the project workplan contract through the Areas of Specialization.
34 | There is a complete record (UNHCR “Right of Use Agreement”) and assets procured by the Partner are generally barcoded, where applicable. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Verify that the list of assets in the project workplan contract terms is complete and up-to-date. Sample a number of assets procured by the partner for the project to verify that they have been subject to item identification control. While the use of barcoded controls is recommended, it's not mandatory. Any evidence of item identification control is acceptable as long as it's well-managed, goods are properly recorded, and easily identifiable. Select the applicable drop-down option: - Yes = There is a complete record of the assets for the project and assets procured by the partner are subject to item identification control. - No = There is not a complete record of the assets for the project and/or assets procured by the partner are not subject to item identification control. Raise an implementation monitoring issue with the category "asset management" and provide a recommendation for the partner to update the asset record and/or start using item identification control for their assets. Assign the issue to the partner for their follow up. Or, select 'No' if this question is not applicable and add a note to the answer to explain that it is not applicable. The partner will not be able to add a note in response to this question but their feedback is not required since it is not applicable. Attach any supporting evidence to the question, for example the complete list of assets from the project workplan contract terms (not mandatory). NB: The question contains an error - there is no standalone "Right of Use Agreement" anymore and there are right of use conditions written into the project workplan contract through the Areas of Specialization.
TOPIC | GOODS FOR DISTRIBUTION TO FORCIBLY DISPLACED AND STATELESS PERSONS
Q # | Question | Type of Answer | Guidance
35 | Partner has procedures in place to store, record, track and safeguard NFIs under its control and ownership, whether purchased with UNHCR funds or not. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No - Not applicable | Ascertain if the partner has procedures in place to store, record, track and safeguard non-food items (NFIs) under its control and ownership, whether purchased with UNHCR funds or not. To effectively manage NFIs, the partner should designate secure storage areas with locked facilities to prevent unauthorized access and ensure systematic organization for easy retrieval. Detailed recording procedures are necessary, as well as maintaining comprehensive records of item descriptions, quantities, and storage locations that are regularly updated to reflect inventory changes. Tracking procedures should be implemented to monitor NFIs throughout their lifecycle, potentially utilizing barcode or RFID technology for accurate tracing. Safeguarding measures, including restricted access controls, surveillance systems, and regular verification, are crucial to prevent loss or damage. Questions to consider include the following: Are the NFIs with a limited shelf-life sufficiently monitored to ensure they do not expire prior to issue? Are the warehouse facilities sufficiently secure, providing suitable conditions for the NFIs held, with adequate protection against environmental factors? Are NFIs maintained in a way that allows authorized persons safe and ready access to them? Is there adequate insurance of warehouses including coverage for fire and theft? Select the applicable drop-down option: - Yes = Partner has procedures in place to store, record, track and safeguard NFIs under its control and ownership, whether purchased with UNHCR funds or not. - No = Partner does not have procedures in place to store, record, track and safeguard NFIs under its control and ownership, whether purchased with UNHCR funds or not. Raise an implementation monitoring issue with the category "goods for distribution" and provide a recommendation for the partner to establish such procedures for NFIs under its control and ownership. Assign the issue to the partner for their follow up. - Not applicable = this question is not applicable because the partner does to have any NFIs under its control and ownership. Attach any supporting evidence to the question (not mandatory).
36 | Partner has an asset management system (including periodic physical counts) that allows stock levels to be optimized & avoids overstocking in distribution centers. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No - Not applicable | Verify if the partner has an asset management system (including periodic physical counts) that allows stock levels to be optimized and avoids overstocking in distribution centers. Review the partner's stock reports for their warehouse(s) and distribution centre(s) and look for any possible trends in the reporting. Questions to consider asking include the following: Are assets managed using the First in First Out (FIFO) approach? The FIFO approach considers the First in Date, the date that the items were received by the partner in any location and not just on the warehouse that currently store those items. Are physical verifications of assets reconciled to the records held on a sufficiently frequent basis, and are the results, including any necessary adjustments, documented and approved? Select the applicable drop-down option: - Yes = Partner has an asset management system (including periodic physical counts) that allows stock levels to be optimized and avoids overstocking in distribution centers. - No = Partner does not have an asset management system (including periodic physical counts) that allows stock levels to be optimized and avoids overstocking in distribution centers. Raise an implementation monitoring issue with the category "goods for distribution" and provide a recommendation for the partner to establish or improve their asset management system to enable stock levels to be optimized and avoid overstocking. Assign the issue to the partner for their follow up. - Not applicable = this question is not applicable because the partner does to have any assets under its control and ownership. Attach any supporting evidence to the question (not mandatory).
TOPIC | BUDGETARY CONTROLS
Q # | Question | Type of Answer | Guidance
37 | Partner has procedures in place to prevent deficits (over commitments, purchases, expenses) to manage cash flow, meet the PW cash needs & monitor level of eligible expenditures to remain within budget flexibility. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Assess whether the partner has procedures in place to prevent deficits (over commitments, purchases, expenses) in order to manage cash flow, meet the project workplan's cash needs and monitor the level of eligible expenditures to remain within the budget flexibility controls (applied at the time the project workplan contract was signed - 30 - 50% budget flexibility between outputs). Examine the partner's documentation regarding deficit prevention, cash flow management, and expenditure monitoring. Ensure these procedures detail specific steps for preventing deficits, managing cash flow to meet the project workplan's cash needs, and monitoring eligible expenditures. Questions to consider include the following: has the partner faced any cash deficits to date for the project and, if so, how were they dealt with? Is the partner meeting the project workplan's cash needs? Have the eligible expenditures reported to date for the project remained within the budget flexibility controls? Select the applicable drop-down option: - Yes = Partner has procedures in place to prevent deficits in order to manage cash flow, meet the project workplan's cash needs and monitor the level of eligible expenditures to remain within budget flexibility. - No = Partner does not have procedures in place to prevent deficits in order to manage cash flow, meet the project workplan's cash needs and/or monitor the level of eligible expenditures to remain within budget flexibility. Raise an implementation monitoring issue with the category "budgetary controls" and provide a recommendation for the partner to establish or improve their procedures to prevent deficits, manage cash flow, meet the PW's cash needs and/or monitor the level of eligible expenditures to remain within budget flexibility. Assign the issue to the partner for their follow up. Attach any supporting evidence to the question (not mandatory).
38 | Partner has effective activity monitoring reports to avoid last minute requests for extension of implementation and/or liquidation periods. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No | Request to see activity monitoring reports from the partner to verify if these reports are effective in avoiding any last minute requests for extension of implementation and/or liquidation periods. Review a sample of meeting minutes from the partner where the agenda included discussions on activity monitoring reports. Questions to consider include the following: does the partner conduct timely reviews of the budget versus costs incurred to date? Do the reports include an overview on the progress made for the project, covering achievements/milestones reached and any delays encountered? Are the reports systematically documented and follow a proper approval process? Select the applicable drop-down option: - Yes = Partner has effective activity monitoring reports to avoid last minute requests for extension of implementation and/or liquidation periods. - No = Partner does not have effective activity monitoring reports to avoid last minute requests for extension of implementation and/or liquidation periods. Raise an implementation monitoring issue with the category "budgetary controls" and provide a recommendation for the partner to either begin creating or improve activity monitoring reports. Assign the issue to the partner for their follow up. Attach any supporting evidence to the question, for example a copy of an activity monitoring report from the partner (not mandatory).
39 | At year end ONLY, Partner has reported expenditures for activities implemented during approved project implementation period (generally end-Dec) & related payments were made within the approved liquidation period. (If ‘No’ - open an ‘Issue’)* | Drop-down menu choice: - Yes - No - Not applicable | This question only applies to year-end reporting. Verify that the partner has reported expenditures for activities implemented during the approved project implementation period (generally by the end of December) and verify that related payments were made within the approved liquidation period. Double check the dates of payments and reported expenditures. Similar cut off issues detected during the year (before the year end PFR) would have a lower impact as related expenditures are eleigible for th next reporting period, which is not the case for the year end PFR. Select the applicable drop-down option: - Yes = Partner has reported expenditures for activities implemented during approved project implementation period and related payments were made within the approved liquidation period. - No = Partner has not reported expenditures for activities implemented during approved project implementation period and/or related payments were not made within the approved liquidation period. Raise an implementation monitoring issue with the category "budgetary controls" and provide a recommendation for the partner to improve their expenditure reporting and/or timing of payments. Assign the issue to the partner for their follow up. - Not applicable = this question is not applicable becuase it is not year-end. Attach any supporting evidence to the question (not mandatory).
40 | Partner has appropriate segregation of duties in place (preparer/reviewer/approver).* | Drop-down menu choice: - Yes - No | Verify if the partner has appropriate segregation of duties in place when it comes to preparing, reviewing and approving financial transactions. A red flag in the segregation of duties for budgetary controls is when the same individual is responsible for both budget planning and budget execution without proper oversight or review. This lack of segregation increases the risk of errors or fraudulent activities, such as inflating budget estimates to justify higher spending or diverting funds for unauthorized purposes. Therefore, it's essential to have clear roles and responsibilities assigned to different individuals or departments and implement appropriate checks and balances to ensure the integrity of budgetary controls. Questions to consider include the following: are the segregation of duties for financial transactions and systems documented by the partner? Are the segregation of duties continuously followed by the partner? Select the applicable drop-down option: - Yes = Partner has appropriate segregation of duties in place. - No = Partner does not have appropriate segregation of duties in place. Raise an implementation monitoring issue with the category "budgetary controls" and provide a recommendation for the partner to establish/improve segregation of duties for financial transactions and systems. Assign the issue to the partner for their follow up. Attach any supporting evidence to the question (not mandatory).
41 | Partner has adequate oversight of activities assigned to third parties and with required approval by UNHCR. (If ‘No’ - open an ‘Issue’)* | Yes / No / N/A | Assess whether the partner has procedures and practices in place for the adequate oversight of activities assigned to third parties for which arrangements have been made to have the approval by UNHCR. Oversight may involve various mechanisms such as an internal committee comprising members from different departments, frequent board meetings, the internal audit department, as well as external auditors. Request to see samples of meeting minutes from the partner's intenal committee / board / audit department as applicable. Select 'Yes' if the partner has adequate oversight of activities assigned to third parties and with required approval by UNHCR. Select 'No' if the partner does not have adequate oversight of activities assigned to third parties and/or the oversight of activities assigned third parties does not have the required approval by UNHCR. Raise an implementation monitoring issue with the category "budgetary controls" and provide a recommendation for the partner to ensure there is oversight of activities assigned to third parties and/or to ensure the oversight has the required approval from UNHCR. Assign the issue to the partner for their follow up. Select 'N/A' if this question is not applicable to the project - i.e. there are no third parties. Attach any supporting evidence to the question (not mandatory).
TOPIC | OTHER PROCEDURES CONDUCTED
Q # | Question | Type of Answer | Guidance
42 | Other procedures conducted and not listed above. | Free text | If applicable, assess the partner's compliance with any other additional project requirements. For example, procedures related to cash-based interventions and IT controls. Write out a summary of the partner's level of compliance with these other procedures. Are there areas where the partner needs to improve on their compliance? Are the documented procedures adequate in scope, clarity and level of detail? If there are no additional project requirements when it comes to compliance and procedures, leave the answer blank (it is not a mandatory question). Attach any supporting evidence to the question (not mandatory).
TOPIC | OTHER SUPPORTING DOCUMENTS
Q # | Question | Type of Answer | Guidance
43 | Other supporting physical evidence was provided, i.e. photographs (if other supporting documents available, attach and provide comments) | Free text | If the partner provided other supporting physical evidence for this financial verification (e.g. photographs), write out a clear description for each piece of physical evidence in the answer to this question and attach copies of the evidence to this question. If no other supporting physical evidence was provided by the partner, leave the answer blank (it is not a mandatory question).
TOPIC | OUTCOME OF THIS VERIFICATION AND ACTION PLAN - UNHCR CAN ADD A NOTE TO ANY OF THE QUESTIONS IN THIS TOPIC IN ORDER TO PROVIDE FURTHER EXPLANATIONS/JUSTIFICATIONS
Q # | Question | Type of Answer | Guidance
44 | Expenditure rate is comparable to results achieved: considering reported actuals against targets, as stipulated within the Project Performance Verification as a % towards each target. (If ‘No,’ provide an explanation and open an ‘Issue’)* | Yes / No | Determine if the expenditure rate is comparable to the results achieved by considering the reported actuals against the targets, as stipulated within the Project Performance Verification (PMC02) as a percentage towards each target. Review the answer to Q18 of the PMC02 where the Programme recorded the most recently recorded progress towards each planned indicator as a percentage (each indicator progress % = each indicator total target divided by the latest reported actual, where relevant). Select 'Yes' if the expenditure rate is aligned with the level of results achieved in the reporting period. Select 'No' if the expenditure rate is not aligned with the level of results achieved in the reporting period and provide a detailed explanation for this selection. Raise an implementation monitoring issue with the category "expenditure comparable to results" and provide a recommendation for the partner to improve their expenditure rate and align it with the level of results achieved. Assign the issue to the partner for their follow-up. Add a note to write out an explanation/justification for the answer selection for this question (not mandatory). Attach any supporting evidence to the question, for example, a screenshot of Q18 from the PMC02 (not mandatory).
45 | Amount of PFR verified is recommended for acceptance* | Yes / No | Select 'Yes' if the verified amounts recorded in the PFR are recommended for acceptance by UNHCR senior management. Select 'No' if the verified amounts recorded in the PFR are not recommended for acceptance by UNHCR senior management. Add a note to write out an explanation/justification for the answer selection for this question (not mandatory). Attach any supporting evidence to the question (not mandatory).
46 | Release of next instalment is recommended* | Yes / No | The release of prepayments is dependent on the amount of the prepayment proportioned with the actual performance of the project (documented in relevant project verifications) and the planned work for the next period according to the project workplan. In case unspent balances or audit recoveries outstanding from the partner are not successfully recovered, the operation is required to deduct the unrecovered amounts from the subsequent prepayment for the partner where applicable, understanding that the partner is then required to report on both the reduced prepayments (UNHCR funds) and the amount deducted (as partner’s repayment). The disbursement of prepayments is subject to the availability of funds, the receipt of an accurate PFR, project performance and financial verifications, planned activities, cash flow and resource requirements for the next months. UNHCR provides prior notification to the partner if there are funding challenges. When the partner requests for the next prepayment, UNHCR considers the unused balance from the previous one. When reviewing a prepayment release, the operation looks at the risk rating of the partner, the progress being made in the project, and the forecasted non-linear expenditure in the coming period. UNHCR disburses the financial allocation for the partner support costs as part of each prepayment transferred to the partner’s bank account, as stipulated in the project workplan. Select 'Yes' if the release of the next prepayment to the partner is recommended to action by UNHCR. Select 'No' if the release of the next prepayment to the partner is not recommended to action by UNHCR or if this question is not applicable because there is no further prepayment to be released. Add a note to write out an explanation/justification for the answer selection for this question (not mandatory). Attach any supporting evidence to the question (not mandatory).
47 | Amount of next instalment requested by Partner* | Free text | Enter the monetary value, inclusive of currency, for the next prepayment that has been requested by the partner and recorded in the "requested" column of the prepayment table within the PFR. Write "not applicable" if there is no further prepayment to be released.
48 | Amount recommended by UNHCR* | Free text | Taking into consideration; a) the amount requested by the partner for their next prepayment, b) how this amount is proportioned with the actual performance of the project and the planned work for the next period and c) the partner's expenditure rate (amongst other factors as applicable - e.g. the operation's general cash flow and resource requirements), enter the final monetary value, inclusive of currency, that project control recommends for the partner's next prepayment. This is the amount that will be reflected in the "approved" column for the prepayment table in the PFR and, once the Representative/delegated authority approves the PFR, this is the amount that will be released to the partner from Cloud ERP. Write "not applicable" if there is no further prepayment to be released.
49 | Please provide an explanation for the installment amount recommended by UNHCR, if this differs from amount requested by Partner* | Free text | If UNHCR's recommended amount for the next prepayment differs from the amount requested by the partner, write out a clear an explanation for the discrepancy. This explanation should outline the rationale behind UNHCR's recommendation, considering factors such as, but not limited to, project performance, the accuracy of the partner's reported expenditures in the PFR, UNHCR's budgetary constraints and cash flow, as well as compliance with funding guidelines. Write "not applicable" if there is no difference in the value of the next prepayment amount between what the partner and UNHCR proposes or if there is no further prepayment to be released.
TOPIC | PREPARED AND SIGNED BY UNHCR
Q # | Question | Type of Answer | Guidance
50 | Name, Title* | Free text | Write out the first name and family name of the UNHCR project control focal point who has filled out this PMC03, as well as their official job title.
51 | Signature* | Free text and Upload Signature: - Draw with mouse - Upload image file | In the free text box, write out the name of the UNHCR project control focal point who has filled out this PMC03. In the 'upload signature' box, the same UNHCR project control focal point uploads their electronic signature by either manually drawing their signature with the mouse or by uploading an image file from their local computer/network.
TOPIC | APPROVED AND SIGNED BY UNHCR
Q # | Question | Type of Answer | Guidance
52 | Name, Title* | Free text | Write out the first name and family name of the most senior UNHCR project control focal point who is responsible for granting internal approval to this PMC03, as well as their official job title.
53 | Signature* | Free text and Upload Signature: - Draw with mouse - Upload image file | In the free text box, write out the name of the most senior UNHCR project control focal point who is responsible for granting internal approval to this PMC03. In the 'upload signature' box, the same most senior UNHCR project control focal point uploads their electronic signature by either manually drawing their signature with the mouse or by uploading an image file from their local computer/network.
TOPIC | SHARED AND SIGNED BY PARTNER
Q # | Question | Type of Answer | Guidance
54 | Partner Acceptance Status | Drop-down menu choice: - Accepted - Accepted with Comments - Not Accepted | The partner selects one of the drop-down options, reflecting their acceptance of the project's financial verification.
55 | Partner Comments | Free text | The partner may write out their general comments the project financial verification here. The partner can also add supporting evidence/documentation, raise additional Issues as and where relevant and/or add notes to any of the questions above.
56 | Name, Title | Free text | Write out the first name and family name of the staff member from the partner organization who conducted the review of this PMC03 and provided the acceptance status, as well as their official job title.
57 | Signature | Free text and Upload Signature: - Draw with mouse - Upload image file | In the free text box, write out the name of the staff member from the partner organization who conducted the review of this PMC03. In the 'upload signature' box, the same reviewer from the partner organization uploads their electronic signature by either manually drawing their signature with the mouse or by uploading an image file from their local computer/network.

## Example
PROJECT FINANCIAL VERIFICATION REPORT- PMC03
Sample pre-populated long form for reference |  | Note: Questions with * are mandatory.
TOPIC | PRELIMINARY INFORMATION
Q # | Question | Response by UNHCR | Response by Partner
1 | Implementer* | Partner ABC
2 | Partner Agreement / Contract* | 12345Y24M654321
3 | Type of Verification?* | On-site
4 | If remote only, please justify | Not applicable
5 | Location of the Financial Verification* | Partner HQ at 45 Compliance Road, City, Country
6 | UNHCR Staff Members Conducting the Financial Verification* | XXX (Project Control Officer)/XXX (Senior Project Control Officer)/ XXX (Supply Officer) / XXX (Programme Officer)
7 | Partner Focal Persons Involved in the Financial Verification* | Partner ABC | First and Last Name - Finance Manager, name@Partner ABC.org, Tel 00 XXX XXXX XXXXX
TOPIC | PURPOSE OF THE FINANCIAL VERIFICATION - COMPLETE ALL THAT APPLY AND SELECT “IMPLEMENTATION MONITORING” AS AN ISSUE TYPE IF YOU NEED TO OPEN AN ISSUE:
Q # | Question | Response by UNHCR | Response by Partner
8 | To verify compliance with the Partnership Framework Agreement and Project Workplan, including Governing Clauses and approved Financial Plan or other applicable requirements. | Yes | A response from the partner is not applicable.
9 | To evaluate whether internal controls are in place and functioning, including payment and bank management, procurement, management of subcontracted partners, personnel engagement & payments, budget & asset management, & general control environment. | Yes | A response from the partner is not applicable.
10 | To evaluate whether the financial expenditure of the project is proceeding in accordance with the last reported actuals/results (outputs). | Yes | A response from the partner is not applicable.
11 | To evaluate the PFR in order to ascertain that it fairly represents the financial situation of the project and that UNHCR funds have been used for the intended purpose. | Yes | A response from the partner is not applicable.
12 | To ensure project expenses are incurred according to agreed Financial Plan, charged to appropriate account codes and budget lines, within allowed limits for intra budget lines transfers. | Yes | A response from the partner is not applicable.
13 | To follow up on any UNHCR-supported project management capacity development activities. | Yes | A response from the partner is not applicable.
14 | Other reasons (please specify) | No other reasons for this financial verification. | A response from the partner is not applicable.
15 | Was the Project Performance Verification completed?* | No, extract and attach "Implementation Monitoring" issues report | Note: Partner ABC has checked the report recently shared on open implementation monitoring Issues. We/partner are happy to confirm that all previous recommendations were implemented and closed except for two recommendations which are progressing well and they will be fully addressed by the end of July 2024.
SCOPE AND FINDINGS: FOR EACH OF THE FOLLOWING, RECOMMENDATIONS MUST BE RAISED WITH AN “IMPLEMENTATION MONITORING” ISSUE. IF ANSWERED ‘YES,’ PLEASE ATTACH RELEVANT SUPPORTING DOCUMENTATION.
TOPIC | ELIGIBILITY OF EXPENSES CLAIMED FOR ACTIVITIES, (PLEASE ATTACH SUPPORTING DOCUMENTS FOR THE TRANSACTIONS/VOUCHERS VERIFIED)
Q # | Question | Response by UNHCR | Response by Partner
16 | Expenses charged to appropriate account codes and outputs, within allowed budget flexibility. (If ‘No’ - open an ‘Issue’)* | Yes
17 | Expenditures are in compliance with the project purpose, for direct project costs and/or agreed direct shared costs, while indirect costs remain part of the Indirect Support Costs. (If ‘No’ - open an ‘Issue’)* | No Raise an Issue and record the following: During the verification, UNHCR received a notification from another donor of partner ABC complaining that the partner had charged their project for 100% of office rent while this should be a shared cost with UNHCR. However, the UNHCR verification team noted also that the PFR related transaction list included payments for the rental of office premises for 20,000 USD. UNHCR discussed the issue with the partner and requested the partner to grant UNHCR access to the transaction list for the project of the other donor. The partner indicated that they were sorry for the error in double charging the rent to both agencies and that this was the only incidence they were aware of. UNHCR compared the transaction listing of the UNHCR project with the other donor's project and confirmed that only the rent was double charged. UNHCR recalculated the correct amount of rent at 50% for 10,000 USD while the other 10,000 USD was deemed as ineligible expenditures. UNHCR recommends the reimbursement of 10,000 USD for the wrongly charged rental costs and for the partner to reimburse also the other donor for the overcharged amount. The partner should reinforce the internal control around computation and allocation of costs to different donors to avoid future incidences of double dipping which may be a red flag for fraudulent transactions. | Note: Partner ABC apologized for the error and committed to transferring the 10,000 USD to UNHCR before end of May 2024 and that they will be in touch with the other donor to clarify the matter and reimburse them for the overcharged amount.
TOPIC | FUNDS/CASH MANAGEMENT
Q # | Question | Response by UNHCR | Response by Partner
18 | Bank statements: related to the project reconcile with balances on the partner cash book (if yes - attach bank statements & general ledger/ transaction list to this question / if no - open an "issue")* | Yes
19 | Bank reconciliations: are performed on a monthly basis (if yes - attach bank reconciliations / if no - open an "issue")* | No Raise an Issue and record the following: Because the partner only performs quarterly reconciliations, recommend that monthly reconciliations are adopted, effective immediately. | Note: Partner ABC will start performing monthly bank reconciliations from now onwards.
20 | Bank reconciliations: procedures to follow up on outstanding cheques are in place (if no - open an "issue")* | No Raise an Issue and record the following: Following discussions, partner ABC confirmed that they don't follow up on outstanding cheques. Indicate that cheques # xx, xxx and xxxx still need to clear the bank account after having been issued for many months (NB: specify for how long - e.g. more than 5 months). Recommend the partner to put in place a process of following up with payees so that they can deposit the cheques timely/urgently. Attachments: Copies of bank reconciliations where old outstanding cheques are still listed. | Note: Partner ABC will implement a monthly process of following up on outstanding cheques. The follow up will be initiated upon reception of bank statements.
21 | Cash management procedures: segregation of duties, cash recipients’ identification, PDM, required documentation, physical cash safeguard measures, surprise cash counts are documented. (If ’No’ - open an ‘Issue’)* | No Raise an Issue and record the following: During the PFR verification, the UNHCR MFT discussed with the partner ABC about their procedure for conducting the petty cash surprise counts and requested copies of the Note for the File (NFF) or the memo summarizing the results of the counts. The partner informed the UNHCR MFT that they don't conduct the petty cash surprise counts. Recommend the partner to put in place a procedure for petty cash surprise counts where an NFF, signed by the team that conducts the exercise, is issued. The team conducting the surprise counts should include a manager who does not have sole access to the petty cash safe. | Note: Partner ABC will update the petty cash management policy to include a procedure covering the periodic petty cash surprise counts.
22 | Reported expenditures: in the currency set out in the Financial Plan or partner applied exchange rates aligned to partnership agreement clauses. (If ’No’ - open an ‘Issue’)* | Yes Attachment: Copy of a summary report for verified sample of transactions.
23 | Has any interest income and miscellaneous revenue earned during the project implementation been properly recorded? (If ’No’ - open an ‘Issue’)* | Yes Attachment: Copy of a summary report for any computation completed for validation of the amounts reported by the partner.
TOPIC | PROCUREMENT
Q # | Question | Response by UNHCR | Response by Partner
24 | The partner complies with their own applicable procurement policies. (If ’No’ - open an ‘Issue’)* | No Raise an Issue and record the following: The partner's procurement policies require that the procurement plan is updated regularly but the partner has not updated it once this year. Recommend that the partner immediately updates the procurement plan and schedules future regular updates in the diary for required partner staff. | Note: Partner ABC will update the procurement plan before the end of next month and will share approved plans with UNHCR in order to close this Issue. Moreover, the head of the procurement unit at Partner ABC will ensure consistency for internal compliance with this policy requirement.
25 | Does the partner have strong procurement processes in place, such as sourcing procedures, segregation of duties, no conflict of interests, expertise and timely delivery of expected quality/quantity? (If ’No’ - open an ‘Issue’)* | No Raise an Issue and record the following: UNHCR supply Officer, as part of the MFT conducting this PFR verification, noted that for the procurement of goods XX (e.g. solar panels) the same finance assistant at Partner ABC conducted the technical and financial evaluations. During follow up discussions with the partner's manager of the procurement unit, the UNHCR supply officer noted also that the partner ABC staff who conducted the technical evaluation did not have the required technical expertise for evaluating the solar panel technical specifications. Recommend the partner to urgently take corrective actions by ensuring there is adequate segregation of duties so that different staff conduct the financial and technical evaluations of bids. Also, recommend that the partner has staff with the required expertise assigned to the technical evaluations. Where there are identified gaps, partner ABC is recommended to provide training to staff. Attachments: Copies of the technical and financial evaluations signed by the same individual. Copies of the CVs/job profiles of the staff that conducted the technical evaluation of the solar panels. | Note: Partner ABC is planning to recruit an experienced procurement officer who will have oversight to ensure adequate segregation of duties during procurement exercises. Partner ABC will liaise with UNHCR supply unit to co-facilitate a training on procurement procedures before the end of June 2024. Partner ABC senior managers will review the concerned procurement of solar panels to ensure that there were no other shortcomings and that the panels ordered were received in a timely manner, in the required quality and that the prices were reasonable.
26 | While reviewing supporting documents: where confirmation had to be sought directly from suppliers for information on the invoices (prices, quantity delivered, name/contact details of suppliers), there were confirmed findings? (If ’Yes’ - open an ‘Issue’)* | No Attachments: A copy of the summary schedule with details for the transactions included in the selected sample of vouchers that have been verified, add related notes on findings
TOPIC | HUMAN RESOURCES AND PAYROLL EXPENSES
Q # | Question | Response by UNHCR | Response by Partner
27 | The Partner complies with their policy/guidance on human resources management. (If ‘No’ - open an ‘Issue’)* | Yes
28 | There is a system for tracking time and attendance of staff (full time and part time) for the time spent on the project and linked to salaries charged to the project. (If ‘No’ - open an ‘Issue’)* | No Raise an Issue and record the following: The partner does not have a system that allows the tracking of time and attendance for full time and part time. Hence, it is not possible to ascertain the correctness of the salaries charged to each project (partner is implementing 3 projects). Recommend that the partner urgently implements a system that allows the tracking of time that staff spend on each project and preferably recommend an automated digital system. | Note: Partner ABC would like to know from UNHCR if there are existing good practices among other humanitarian organizations that partner ABC can implement. Initially, partner ABC will implement a manual system to be in place in the next 2 weeks while we explore a long term automated digital solution.
29 | General ledger payroll versus PFR: confirm amount charged to a project for selected staff does not exceed what the Partner is contractually/legally obliged to pay. Supporting documents for salary calculation is in place. (If ‘No’ - open an ‘Issue’)* | Yes
30 | Assess staff existence & salary received: select sample staff members & verify employment records; review benefits (net pay) received versus reported (salary slips) & enquire if any pay back was requested by the Partner. (If ‘No’ - open an ‘Issue’)* | No Raise an Issue and record the following: During verification, 25 staff positions were included in the randomly selected sample, of which some were senior management positions. This represented 15% of the positions listed on the staff lists for the payroll of the first 3 months covered by the PFR. UNHCR checked the recruitment files, the calculation of the salaries and supporting documents (including staff contracts, attendance/timesheets, salary benefits and deduction, pay slips, bank statements) and no issues were reported as all appeared to be in order. In addition, when the verification team contacted the selected staff to confirm the net pay received in their bank accounts, they also discussed if there are practices of staff members being required to remit some amount back to the partner in cash or by bank transfers and all was clear as the UNHCR team did not note any concerns from the staff contacted. In addition, following the issue of double dipping for rental costs discussed earlier, the UNHCR team checked if any staff was also working for other donors and reviewed the name of staff payments as per the other donors transaction list shared by the partner against the staff list for staff working on the UNHCR project. UNHCR confirmed that none was engaged with the other donor, hence the risk for double dipping in personnel costs was not likely. However, the verification team noted that the required government salary deductions/tax had not been remitted to the government for the last 3 months. Recommend that the partner urgently remits to the government all the payroll taxes that have been deducted from the staff and are yet to be paid to the government to avoid potential penalties. Add that the partner should have a procedure in place for allowing the timely remittances of such payroll deductions. | Note: The partner appreciates the work of the UNHCR verification team and the feedback provided. The partner regrets the oversight in delays to pay to the government the payroll related taxes which was partially the result of the late prepayment received from UNHCR late in January. We are making urgently arrangements to ensure the concerned funds are transferred to the tax authorities before the end of next week. When completed, we will be able to provide evidence including Government payroll deduction remittance forms and copies of bank transfers for the payment to the government (or bank statements).
TOPIC | FINANCIAL AND PROJECT RECORDS
Q # | Question | Response by UNHCR | Response by Partner
31 | Confirm whether financial and project records are properly maintained and well organized, and that the accounting system complies with the requirements of the Project Workplan. (‘No’ - open an ‘Issue’)* | Yes
32 | Does the Partner rely on paper/Excel based accounting system? (‘No’ - open an ‘Issue’). Recommendation for acquisition of affordable software could be suggested, if applicable.* | Yes Raise an Issue and record the following: Recommend the partner to use an affordable digital accounting software. | Note: Partner ABC will purchase an accounting software asap following consultations with other humanitarian organizations operating in the region to ensure that we select a product that is mostly used by peers. This will facilitate access to training and benefiting from experiences from peers.
TOPIC | ASSET MANAGEMENT - WITHIN THE MFT OR RELEVANT UNIT I.E. SUPPLY AS APPLICABLE
Q # | Question | Response by UNHCR | Response by Partner
33 | Partner has procedures in place to store, record and safeguard assets under its responsibility, whether purchased from funds provided by UNHCR or provided under a “Right of Use Agreement”. (‘No’ - open an ‘Issue’)* | Yes
34 | There is a complete record (UNHCR “Right of Use Agreement”) and assets procured by the Partner are generally barcoded, where applicable. (If ‘No’ - open an ‘Issue’)* | No Raise an Issue and record the following: A small sample of 15 items listed on the partner's assets reports was selected. These were the items with the top highest values of above 50,000 USD each. The verification team noted that there was no system to identify these items such as a bar code that would easily allow the tracking of items and improved inventory management. Recommend that the partner considers using an asset tracking system which encompasses barcoding. | Note: The partner takes note of the recommendation and will update the SOP on asset management to incorporate procedures on asset tracking including the use of a barcode system. When ready, we will share a copy of the revised SOP and photos of 3 barcoded items from the list of items concerned with this issue.
TOPIC | GOODS FOR DISTRIBUTION TO FORCIBLY DISPLACED AND STATELESS PERSONS
Q # | Question | Response by UNHCR | Response by Partner
35 | Partner has procedures in place to store, record, track and safeguard NFIs under its control and ownership, whether purchased with UNHCR funds or not. (If ‘No’ - open an ‘Issue’)* | No Raise an Issue and record the following: The partner has appropriate arrangements for storing non-food items (NFIs). However, the insurance does not cover the warehouse for potential thefts of NFIs or fire. Recommend that the partner consider including fire and theft for coverage in the warehouse insurance contract. | Note: The partner has been in touch with different insurance companies operating in the region for the possibility of them covering the warehouse for fire and theft. Unfortunately, none of these companies cover for such risks and therefore it is not feasible in the context. As a mitigation measures, we will increase the number of security guards from 5 to 8 guards and will have fire extinguishers serviced regularly and accessible 24/7. Attachments: Communications with insurance companies including their letters confirming that the services are not available.
36 | Partner has an asset management system (including periodic physical counts) that allows stock levels to be optimized & avoids overstocking in distribution centers. (If ‘No’ - open an ‘Issue’)* | No Raise an Issue and record the following: During November 2023 physical verification of assets, 40% (600,000 USD in value) of assets that were to be distributed to forcibly displaced and stateless persons were still in the distribution center. UNHCR had agreed with the partner that such items were to be distributed as soon as received and, at this time of year in Q1 2024/end of March 2024, the expected stock level was to be around 15%, however from the distribution reports received, the verification team noted that 25% of these items are still not distributed. Recommend that the partner reviews the distribution capacities and related procedures to ensure items are distributed timely and avoid overstocking items. | Note: The delays were caused by heavy rain during the month of October 2023 which significantly slowed down the transportation of items from the distribution centers as the road were difficult to navigate. We have not changed the agreed SOP because it already states that items need to be distributed as soon as they are received.
TOPIC | BUDGETARY CONTROLS
Q # | Question | Response by UNHCR | Response by Partner
37 | Partner has procedures in place to prevent deficits (over commitments, purchases, expenses) to manage cash flow, meet the PW cash needs & monitor level of eligible expenditures to remain within budget flexibility. (If ‘No’ - open an ‘Issue’)* | Yes
38 | Partner has effective activity monitoring reports to avoid last minute requests for extension of implementation and/or liquidation periods. (If ‘No’ - open an ‘Issue’)* | No Raise an Issue and record the following: The UNHCR MFT conducting the verification noted that the partner's monitoring reports are very delayed and up to several months in same cases. In addition, UNHCR was aware that at the end of last year's implementation period the partner informed UNHCR very late that some activities were delayed and they were asking for an extension of the implementation period. Recommend that the partner improves on reporting and monitoring of activities in accordance with the agreed timelines as per the project workplan. | Note: The project monitoring team has faced many challenges including long periods of absences for health reasons for 2 key personnel. This has caused unusual delays during the 2023 Q4 and 2024 Q1. As the team is now operating at full capacity these issues will be avoided for the remainder of the 2024.
39 | At year end ONLY, Partner has reported expenditures for activities implemented during approved project implementation period (generally end-Dec) & related payments were made within the approved liquidation period. (If ‘No’ - open an ‘Issue’)* | Yes
40 | Partner has appropriate segregation of duties in place (preparer/reviewer/approver).* | No Raise an Issue and record the following: As noted earlier about the procurement of solar panels, there was no segregation of duties for the bid management. In addition, when verifying the payments issued to senior management it was noted that the head of finance approved the travel request for their own mission, as well as approving the bank transfers to self and later approved the bank reconciliations. This senior manager had therefore performed incompatible duties and the risk for fraud or errors in such contexts is heightened. Recommend that the partner reinforces the internal controls to ensure that there is an appropriate level of segregation of duties. | Note: Unfortunately the cases noted were for the time where other managers where on leave and it was not possible to wait for them to be back. We will make sure that such practices are avoided by better planning to ensure there is a back up system for staff during their leaves of absence.
41 | Partner has adequate oversight of activities assigned to third parties and with required approval by UNHCR. (If ‘No’ - open an ‘Issue’)* | N/A
TOPIC | OTHER PROCEDURES CONDUCTED
Q # | Question | Response by UNHCR | Response by Partner
42 | Other procedures conducted and not listed above. | Not applicable
TOPIC | OTHER SUPPORTING DOCUMENTS
Q # | Question | Response by UNHCR | Response by Partner
43 | Other supporting physical evidence was provided, i.e. photographs (if other supporting documents available, attach and provide comments) | Photo #1: Curing of second floor concrete slab taken on 11th March 2024. Photo #2: Windows installed in ground floor kitchen taken on 14th March 2024. Photo #3: Plumbing installed in ground floor shower and latrine block taken on 14th March 2024. Attachments: 3 photos showing the construction progress to date.
TOPIC | OUTCOME OF THIS VERIFICATION AND ACTION PLAN
Q # | Question | Response by UNHCR | Response by Partner
44 | Expenditure rate is comparable to results achieved: considering reported actuals against targets, as stipulated within the Project Performance Verification as a % towards each target. (If ‘No,’ provide an explanation and open an ‘Issue’)* | Yes Note: The year to date accumulated expenditures (including the current PFR) amounts to 55% of the total budget. From the PMC02, we noted that there are no concerns as it confirms that the implementation progress is proceeding as planned and on time. The validated results against targets indicate an overall progress of 60%.
45 | Amount of PFR verified is recommended for acceptance* | Yes Note: The total PFR submitted was 900,000. From the verification, an amount of 50,000 is rejected. Hence 850,000 is recommended for acceptance.
46 | Release of next instalment is recommended* | Yes Note: It is recommended to release the next prepayment to the partner. The amount to release is adjusted as explained below.
47 | Amount of next instalment requested by Partner* | 850,000 USD
48 | Amount recommended by UNHCR* | 700,000 USD
49 | Please provide an explanation for the installment amount recommended by UNHCR, if this differs from amount requested by Partner* | The amount recommended by UNHCR is 150,000 USD less than the partner's request because the partner still has significant balance from the prior prepayment (more than 1/6 of the total financial plan which is 150,000 USD).
TOPIC | PREPARED AND SIGNED BY UNHCR
Q # | Question | Response by UNHCR
50 | Name, Title* | XXXXX, Project Control Officer
51 | Signature*
TOPIC | APPROVED AND SIGNED BY UNHCR
Q # | Question | Response by UNHCR
52 | Name, Title* | XXXXX, Senior Project Control Officer
53 | Signature*
TOPIC | SHARED AND SIGNED BY PARTNER
Q # | Question | Response by UNHCR
54 | Partner Acceptance Status | Accepted with comments
55 | Partner Comments | Comments from partner: We appreciate the collaboration with the UNHCR financial verification team and the detailed feedback received. We will do our best to close all raised recommendations in a timely manner as requested for each concerned process/question.
56 | Name, Title | XXXXXX, Project Manager
57 | Signature